|  |  |  |  |
| --- | --- | --- | --- |
|  | **Radiocommunication Study Groups** | |  |
| **INTERNATIONAL TELECOMMUNICATION UNION** | |  | |
|  | |  | |
| Source: Document 5A/TEMP/84 | | **Annex 13 to Document 5A/298-E** | |
| **21 November 2016** | |
| **English only** | |
| Annex 13 to Working Party 5A Chairman’s Report | | | |
| DRAFT workplan for wrc-19 agenda item 9.1 Issue 9.1.5 | | | |
|  | | | |

Working Party 5A (WP 5A) was identified by CPM19-1 as the responsible group for WRC-19 agenda item 9.1 – issue 9.1.5 as follows:

9.*1.5* Resolution **764 (WRC‑15)** – *Consideration of the technical and regulatory impacts of referencing Recommendations ITU-R M.1638-1 and ITU-R M.1849-1 in Nos.****5.447F*** *and* ***5.450A*** *of the Radio Regulations;*

It should be understood that this Work Plan is a “living document” and would need to be revised and updated, as appropriate, at every Working Party 5A meeting.

16th Meeting of WP 5A (May 2016)

– Initial discussions on the issue to be studied.

– Develop initial drafts for the CPM text and the workplan.

17th Meeting of WP 5A (November 2016)

– Discuss technical and regulatory impacts as described in Resolution **764 (WRC‑15).**

– Initiate development of working documents as appropriate.

– Consider the need for liaison with the concerned groups.

– Develop elements of draft CPM text based on input contributions, as appropriate.

18th Meeting of WP 5A (May 2017)

– Further discuss the issues as described in Resolution **764 (WRC‑15).**

– Further develop working documents as appropriate.

– Further develop the draft CPM text.

19th Meeting of WP 5A (November 2017)

– Further discuss the issues as described in Resolution **764 (WRC‑15).**

– Further develop working documents as appropriate.

– Further develop the draft CPM text.

– Consider the need for further liaison with the concerned groups.

20th Meeting of WP 5A (May 2018)

– Complete discussions on the issues as described in Resolution **764 (WRC‑15)**.

– Finalize draft CPM text.

– Submit draft CPM text to chapter rapporteur.