|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document 5A/TEMP/271  Subject: WRC-19 agenda item 1.12 Resolution 237 (WRC-15) | **Annex 9 to**  **Document 5A/650-E** |
| **17 November 2017** |
| **English only** |
| Annex 9 to Working Party 5A Chairman’s Report | |
| work plan for WRC-19 Agenda item 1.12 | |
|  | |

| Working Party 5A/Meeting | Work plan |
| --- | --- |
| 16th meeting  May 2016 | WP 5A, based on input contributions, develop and adopt a work plan, including:  – continue developing the PDN Report ITU-R M.[ITS USAGE]  (relevant parts thereof maybe referenced in the CPM Text);  – review of relevant existing ITS Recommendations and Reports (relevant parts thereof maybe referenced in the CPM Text);  – review of relevant existing standards and on-going ITS standardisation activities;  – develop initial draft CPM Text outline;  – liaise as needed with concerned groups requesting further information. |
| 17th meeting  November 2016 | WP 5A, based on input contributions,  – continue developing the PDN Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced in the CPM Text);  – review of relevant existing standards and on-going ITS standardisation activities;  – working on draft CPM Text outline;  – liaise as needed with concerned groups on progress;  – update work plan as needed. |
| 18th meeting  May 2017 | WP 5A, based on input contributions,  – continue developing the PDN Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced in the CPM Text);  – initiating work on a working document towards preliminary draft new Recommendation on ITU-R M.[ITS\_FRQ];  – review of relevant existing standards and on-going ITS standardisation activities;  – continue working on draft CPM Text;  – liaise as needed with concerned groups on progress;  – update work plan as needed. |
| 19th meeting  November 2017 | WP 5A, based on input contributions,  – continue working on the draft new Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced within CPM Text);  – continue working on draft Recommendation on  ITU-R M.[ITS\_FRQ];  – continue working on draft CPM Text;  – update work plan as needed. |
| 20th meeting  May 2018 | WP 5A, based on input contributions,  – continue working on the draft new Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced within CPM Text);  – finalize work on a draft new Recommendation ITU-R M.[ITS\_FRQ] and submit to SG 5 meeting for approval;  – finalize draft CPM Text and send to CPM management team;  – update work plan as needed. |
| 21st meeting  [November 2018] | WP 5A, based on input contributions,  – finalize work on draft new Report ITU-R M.[ITS USAGE] and submit to SG 5 meeting for approval (relevant parts thereof maybe referenced in the CPM Text);  – update work plan as needed. |