|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Annex 5 to Document [5A/221](https://www.itu.int/md/R19-WP5A-C-0221/en) | **Annex 5 to Document 5A/359-E** |
| **11 May 2021** |
| **English only** |
| Annex 5 to Working Party 5A Chairman’s Report | |
| WORKPLAN/REPORT FOR WRC-23 Agenda Item 1.3 | |
|  | |

*[Note: The finalization date is of indicative nature as it will depend on the progress of work and the extent of any possible contributions. This workplan may therefore be adjusted at each meeting. Furthermore, the prevailing situation and circumstances might impact the workplan.]*

*[Note: This work plan will be reflected as Annex 5 of the WP5A Chairman’s Report. At each meeting of WP5A the work plan for that particular meeting is converted to a report of the activities undertaken during that meeting.]*

| Working Party 5A meetings | Activity |
| --- | --- |
| 1st meeting of the study cycle  (23rd meeting of WP5A)  July 2020 | • Consider input contributions;  • Develop initial work plan;  • Develop liaison statement to contributing groups;  • Create placeholder for draft CPM text. |
| 2nd meeting of the study cycle  (24th meeting of WP5A)  November 2020 | • Consider input contributions;  • Consider the work plan for this agenda item and suggest necessary changes based on input contributions;  • Prepare the compilation of parameters/criteria received in response to liaison statements and contributions to WP5A, if any;  • Analyse existing ITU-R Reports and/or Recommendations that may be relevant to the sharing and compatibility studies;  • Develop initial version of draft CPM text based on input contributions;  • Consider need for further liaison statements. |
| 3rd meeting of the study cycle  (25th meeting of WP5A)  May 2021 | • Consider input contributions;  • Continue the analysis of existing ITU-R Reports and/or Recommendations, and of any new parameters/criteria received;  • Initiate work on a working document on any additional sharing and compatibility studies, if necessary, based on input contributions;  • Further develop draft CPM text based on input contribution;  • Liaise with contributing Working Parties regarding characteristics and protection criteria for this agenda item, as and if needed;  • Revise the work plan, as necessary. |
| *Disclaimer note: The objectives of work plans mentioned below are informative at this stage and need to be carefully reviewed during the third meeting, as well as being subject to review at subsequent meetings.* | |
| 4th meeting of the study cycle  (26th meeting of WP5A)  November 2021 | • Consider input contributions;  • Finalise the analysis of existing ITU-R Reports and/or Recommendations, and of any new parameters/criteria received;  • Continue the working document on any additional sharing and compatibility studies, if necessary, based on input contributions;  • Continue drafting CPM text based on input contributions. |
| 5th meeting of the study cycle  (27th meeting of WP5A)  May 2022 | • Consider input contributions;  • Continue the working document on any additional sharing and compatibility studies, if necessary, based on input contributions;  • Continue drafting CPM text based on input contributions. |
| 6th meeting of the study cycle  (28th meeting of WP5A)  November 2022  *(if pre-CPM deadline)* | • Consider input contributions;  • Finalize the working document on any additional sharing and compatibility studies, if necessary, based on input contributions;  • Finalize the work on draft CPM text and submit to Chapter Rapporteur. |