## Slide 1: Process and timetable for The elaboration of the ITU STRATEGIC and financial PLANs for 2020-2023 3rd Meeting of the Council Working Group for Strategic and Financial Plans for 2020-2023
15-16 January 2018
Document CWG-SFP-3/8-E 5 December 2017 Original: English

## Slide 2: Process for the 2020-2023 strategic plan
CWG-SFP
C17
C18
PP18
SG provides input to Council
(No.74A, Constitution)
Council shall initiate the
preparation of a draft SP
(e.g. by creating a CWG)
(No. 62A, Convention)
Draft
SP
CWG coordinates the elaboration of the
draft SP
(Res. 1384 / C17)
Final
Draft
SP
Member States
Sector Members
Advisory Groups
Provide input for the preparation of a draft SP
(No. 62A, Convention)
SG coordinates the Implementation of the SP
(No.86A c) bis, Convention)
Strategic
Plan
2020-2023
Adopts the
Strategic Plan for
the Union
(No.51, Constitution)
Secretariat
Secretariat
WTDC-17 contribution
Open and public consultations
Notes: Council 2017 initiated the process for the preparation of the new draft Strategic Plan, by establishing the CWG for the elaboration of the Strategic and Financial Plans 2020-2023
The process is similar to the process followed for the elaboration of the current (2016-2019) plans
The CWG is open to Member States and Sector Members as well –and will receive inputs also from the Sector Advisory Groups and WTDC-17, as well as open and public consultation (as per the previous cycle)
The First Public Consultation and a Staff Survey have already taken place.
Following the work of the CWG, the Draft Strategic Plan will be submitted to the 2018 Session of Council, which will review and forward to PP-18
It is a membership driven, open and transparent process to which Member States, Sector Members, regional organizations, etc. are invited to contribute at all stages.

## Slide 3: Timetable for the elaboration of the 2020-2023 strategic and financial plans
Date | Milestone
2017 Session of Council | Establishment of the CWG-SFP
23 May 2017 | 1st meeting of CWG-SFP
Jun – Aug 2017 | Preparation of the secretariat’s input, including: - Public consultation of the CWG-SFP on the strategic priorities - Strategic planning workshops within the ITU secretariat
11-12 Sep 2017 | 2nd meeting of CWG-SFP
9-20 October 2017 | WTDC-17 contribution to the ITU Strategic Plan
October - December 2017 | Drafting the text of the Strategic Plan
15-16 Jan 2018 | 3rd meeting of CWG-SFP - Draft Strategic Plan discussed - Draft proposals for revised Resolutions discussed - Draft Financial Plan discussed at CWG-FHR
February – March 2018 | Public consultation on the draft strategic plan
Q1-Q2 2018 (tbc) | Input from RAG / TSAG / TDAG meetings
16 April 2018 | 4th meeting (before the 2018 Session of Council)
17-27 April 2018 | Council 2018
End of June 2018 | Final draft Strategic and Financial Plans submitted to PP-18
29 Oct – 16 Nov 2018 | Adoption of the Strategic and Financial Plans by PP-18