|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2017-2020 |  |  | TSAG-TD789 |
| --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |
|  |  |  |  | Original: English |
| Question(s): |  |  | N/A | E-Meeting, 21-25 September 2020 |
| TD |  |  |  |  |
| Source: |  |  | Director, TSB |  |
| Title: |  |  | Action plan related to the Resolutions and Opinion of WTSA-16 |  |
| Purpose: |  |  | Discussion |  |
| Contact: |  | Martin Euchner TSB |  | Tel: +41 22 730 5866 Fax: +41 22 730 5853 E-mail: martin.euchner@itu.int |

| Keywords: | WTSA-16 Action Plan; |
| --- | --- |
| Abstract: | The WTSA-16 Action Plan is a monitoring and reporting tool to keep track of the implementation of WTSA-16 Resolutions and Opinion. This document contains the WTSA-16 Action Plan that has been updated since January 2020. |

Action:	TSAG is invited to discuss the WTSA-16 Action Plan.

Background

WTSA-16 (Hammamet, 25 October – 3 November 2016) approved 61 new or revised Resolutions. In order to keep track of the implementation of so many Resolutions, TSB developed and maintained a WTSA Action Plan (see https://www.itu.int/en/ITU-T/wtsa16/Documents/WTSA-Action-Plan/WTSA-ActionPlan-201609.zip) as a monitoring and reporting tool during the last 2013-2016 Study Period (see WTSA-16 Doc.35 - WTSA-12 Action Plan).

Executive summary

This document further updates the action plan for the WTSA-16 Resolutions (from December 2020 TSAG-TD657) to be maintained and progressed through this study period.

The Action Plan details 366 action items, their associated responsibilities, necessary collaborations, reports and current status.

This document contains two attachments

- a WORD document which details the implementation progress report;

- and an EXCEL sheet which illustrates the implementation status of each action item, and statistics.

# Note: Any box with a small red triangle in the upper right corner has a Comment. Moving the cursor over the box will display the comment. The comment of each ‘Action required’ box is the extraction of the operational part of the Resolution.

The WORD report is based on WTSA-16 C 0035 which was the final version of the action plan for the study period 2013-2016 as provided to WTSA-16, and has been updated to include further developments since September 2016.

The EXCEL sheet allows all action items to be displayed on a single sheet, or sorted by any of the columns, such as all those for TSB action, or all those requiring a report to Council, etc. It also uses colours to visualize the completion status of action items. The EXCEL sheet illustrates the implementation of action items in figures:

- In summary, this Action Plan contains 366 detailed action items for the 61 WTSA-16 Resolutions.

- TSB/TSBDir is responsible for 210 action items, and Membership is responsible for 156 action items.

Assessment of the implementation of WTSA resolutions

WSTA-16 Resolution 83 instructs the TSB Director to assess the implementation of WTSA resolutions by all parties concerned.

The action plan categorizes the status of the action items into four types depending on progress:

- Complete: The action item is considered complete and met its goals.

- Ongoing by nature with periodic goals met: The action item has been progressing well according to its reported achievement.

- Ongoing: The action item typically is under consideration, but needs more time and efforts for its progression or its reporting; or is waiting to be started.

- No action / needs attention: The action item has not made any necessary progress and deserves attention.

As of 18 September 2020

  - 15 action items are one-time actions with measurable milestone/criteria, and have already been fully implemented and can be considered complete (4% of all).

  - 332 action items are ongoing by nature with certain/some/significant progress achieved or periodical goals met (91%).

  - 10 action items are ongoing/pending by nature (3%).

  - 9 action items are identified not to have had any activity so far or require attention (2%).
It is to be noted that the TSB Director took significant efforts to take action on formerly red-labeled action items under responsibility of the TSB Director requiring attention, with the positive outcome, that only one remaining action item could not be resolved.

Note, that the attached excel sheet provides more detailed statistics for the status of the action items with respect to the responsibilities of TSB/TSBDir and Membership.

It is planned to further maintain this action plan throughout this 2017-2020 study period and to provide updates at the forthcoming TSAG meeting.

Attachments: 2

- WTSA-16 Action Plan V0.8 - Progress Report in WINWORD

- WTSA-16 Action Plan V0.8 - EXCEL sheet.

_________________

_______________