|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A black and white logo  Description automatically generated with low confidence | INTERNATIONAL TELECOMMUNICATION UNION  **TELECOMMUNICATION STANDARDIZATION SECTOR**  STUDY PERIOD 2022-2024 | | | | TSAG-TD152R1 |
| TSAG |
| Original: English |
| **Question(s):** | | RG-WPR | | | Geneva, 12-16 December 2022 |
| **TD** | | | | | |
| **Source:** | | Rapporteur and Associate Rapporteur, RG-WPR | | | |
| **Title:** | | Proposed project plan to implement the action plan for the analysis of ITU-T study group restructuring | | | |
| **Contact:** | | | Greg Ratta | Tel: +1 202 482 0499 E-mail: [gratta@ntia.gov](mailto:gratta@ntia.gov) | |

|  |  |
| --- | --- |
| **Abstract:** | This TD presents the proposed project plan to implement the action plan for the analysis of ITU-T study group restructuring. |

**Introduction**

In the initial meeting of RG-WPR, the participants requested to view the intended plan to implement the action plan for the analysis of ITU-T study group restructuring. This TD presents a draft of that project plan for the consideration and concurrence, if appropriate, by the participants of this rapporteur group.

**Discussion**

The high-level plan is to begin with the collection of the data (metrics) identified in the action plan, closely followed by and in parallel with the definition of the KPIs (how to use the data) for reporting to TSAG by June 2023. After achieving consensus on the data and how to use it, consider proposals for the structure of ITU-T, with an objective of completing the report of this activity in time for the June 2024 TSAG meeting. The following figure shows this plan.

Chart

Description automatically generated

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_