| INTERNATIONAL TELECOMMUNICATION UNION |  |  |  |
| --- | --- | --- | --- |
|  | COUNCIL |  | Document C04/10-E 12 March 2004 Original: English |
| GENEVA — SESSION 2004 — (9-18 JUNE) |  |  |  |

| Report by the Secretary-General |  |
| --- | --- |
| 1 Subject: | ITU-T DRAFT operational plan for 2004-2007 |

| 2 Purpose This document presents the Operational Plan of the Telecommunication Standardization Sector for the period 2004-2007. |  | Ref. doc. |
| --- | --- | --- |
| 3 Background Under Article 15, No. 205A of the Convention, the Director of the Telecommunication Standardization Bureau is requested to prepare annually, for review by the telecommunication standardization advisory group, and then for review and approval by Council, a four-year rolling operational plan of activities to be undertaken by the staff of the TSB. |  | CV 205A |
| 4 Recommendation The Council is invited, after having reviewed the Operational Plan of activities of the Telecommunication Standardization Sector for the period 2004-2007, to approve the attached draft Resolution in Annex A. |  |  |
| 5 Implications |  |  |

Yoshio UTSUMI
	Secretary-General

Director, Telecommunication Standardization Bureau

- ITU-T Operational Plan for 2004,2005, 2006, 2007. 
Linkage between Strategic, Financial and Operational Planning

- (Resolution 72; Rev. Marrakesh, 2002)

- ITU-T Operational Plan for 2004,2005, 2006, 2007. 
Linkage between Strategic, Financial and Operational Planning.(Resolution 72; Rev. Marrakesh, 2002)

- [Update 10 March 2004]

# History of the document

- At the TSAG meeting 10-14 November 2003, TSB presented TD 226, “ITU-T Operational Plan for 2004 and 2005 – Linkage between Strategic, Financial and Operational Planning. Outlook for 2006-2007.” TSAG endorsed the Operational Plan 2004 and took note of the Operational Plan for 2005. The current document presents an update of the ITU-T Operational Plan and takes into account the decisions of the Additional Council (27-29 October 2003) and the advice received from TSAG in November 2003. The most significant changes and additions are:

- A much more detailed plan for the years 2006 and 2007 (Annexes 5 – 8 are new) has been given to fulfill the requirement for a 4-year rolling Operational Plan, even though forecasts are difficult before knowing the results of WTSA 2004. The plans for 2006 and 2007 are based on the status quo.

- Appropriations for TSAG have been amended in order to be able to finance a second meeting in 2005.

Budget for the biennium 2004-2005

The ITU-T budget for the biennium 2004-2005 is CHF 25,795,000, compared with CHF 28,813,000 in 2002-2003. Nominally, the decrease amounts to 10.47 %, but taking into account the programme variation due to the venue of WTSA-04 (budgeted with 566.000 CHF), the cost increase due to UN-salary increases and the rise in the consumer index price, in real terms the decrease corresponds to 15.76 %.

To reach the financial target, a combination of savings and efficiency measures is being implemented:

- Reduced postal document dispatch costs: – 628.000 CHF

- A decrease of the variable appropriations for Study Group documentation by – 1.812.000 CHF due to increased use of electronic document handling (this part is entirely in the ITU-T budget), comprising a reduction in translation (–17% in volume for English, French and Spanish documents), typing (–54% in volume) and reprography (–63% in volume).

- A cut of 10 % in TSB staff-months capacity. TSB-staff foreseen for 2004 is 23 P-staff and 40.5 G-staff, yielding a total 63.5.

- A cut of 50 % (= –100.000 CHF) in fellowships granted to attend Study Group 3 meetings (a cut of 90% was initially forecast in February 2003 but not accepted by TSAG) and holding three Study Group 3 meetings per biennium instead of four.

- Reductions in TSAG, Study Group and Bureau expenditure items of –1.044.000 CHF.

- In the ITU-T budget for 2004-2005, Sector Members’ financial contributions have dropped.  Their number of contributory units is foreseen at 175 (22.050.000 CHF) as against 206 ½ (26.019.000 CHF) in the 2002-2003 budget (-15%).

- On the contrary, there is an important increase in the contributions from Associates, 56 units (1.176.000 CHF) in the proposed 2004-2005 budget as compared to 3 units (63.000 CHF) in the 2002-2003 budget (+1767%).

Operational Plan 2004

The budget for 2004 is 13.199.000 CHF. Details of the Operational Plan 2004 are contained in Annex 1 and 2.

WTSA-04

Brazil will host WTSA from 5-14 October 2004 in Florianópolis. The agreement was signed on 24 September 2003 between the Federative Republic of Brazil and ITU. Subsequently, an invitation letter dated 27 October was sent out.  In addition, the relevant TSB Circular 221 of 25 February 2004 was also sent out.

TSB will organize or participate in  “WTSA Regional Consultation Sessions” in the regions in the first half of 2004, with the goal to improve the participation in, and effectiveness of, the Assembly in accordance with Resolution 25, “Strengthening the regional presence” (Rev. Marrakesh, 2002).

Cybersecurity Symposium

A “Cybersecurity Symposium” will take place on 4 October 2004 in Florianópolis, Brazil, i.e. one day prior to WTSA-04. A Steering Committee is currently planning the details of the event. The event will center aorund the following themes: “Cybersecurity threats – what are the issues?”, “Experiences with and responses to Cybersecurity Threats”, and “Standards, policy, regulatory, and legal aspects”.

ITU-T’s “Security Manual”

ITU-T has been active in security in telecommunications and information technology for many years. However, it may not have always been easy to find out what has been covered, and where it can be found.

To remedy this situation, TSB has issued, in collaboration with some experts of ITU-T, an 88-page “Security Manual”.  The purpose of the manual is to highlight and offer a bird’s eye view of the numerous Recommendations developed by ITU-T to secure the communication infrastructure and associated services and applications. The manual focuses on completed work, not on work in progress or upcoming work.

The entire Security Manual (1st Edition) may be found at http://www.itu.int/ITU-T/edh/files/security-manual.pdf.

A 2nd Edition, updated and enhanced, is in the making for the Cybersecurity Symposium on 4 October 2004.

TSAG

Appropriations allow for three TSAG meetings in 2004-2005.

Study Groups

2004, the number of ITU-T Groups is the same as in 2003 (12 Study Groups, 1 Special Study Group and TSAG), generating with close to 200 Questions and around 300 ITU-T texts (recommendations, amendments, corrigenda) about the same output as in 2003. The plan includes support to Study Groups by applying leading-edge formal methods to normative text in ITU-T Recommendations.

Workshops and Seminars

The ITU-T Workshop Program is being molded into an integral part of ITU-T’s activities. Workshops disseminate expert knowledge on state-of-the-art technologies and address an audience that reaches beyond pure standardization people. Workshops not only attract new attendees, but also explore new standardization areas for ITU-T. We are optimistic that the success of the workshop program 2003 (e.g., several new Questions were created and new Rapporteurs recruited as a consequence of workshops) will be continued in 2004.

Among the workshops in 2004 (past and confirmed) are:

- ITU Seminar on Standardization, Cambodia, 11-13 February 2004

- High-level workshop on International Standards for Medical Technologies, a joint workshop of ISO, IEC and ITU-T in partnership with WHO (World Health Organization), Geneva, 26-27 February 2004.

- Workshop on use of UML for ODP and ITU-T languages, Geneva, 14 March 2004.

- Workshop on H.350 Directory services for multimedia networks, Purdue University, USA, 25 March 2004.

- ITU Seminar on Standardization, Ghana, mid-April 2004

- Workshop on convergent regulation – is it becoming technology-neutral?, Geneva, 17 May 2004.

- All Star Network Access Workshop, Geneva, 2-4 June 2004.

- Home networking and home services workshop, Japan, 16-18 June 2004

- Cybersecurity Symposium, Florianópolis, Brazil, 4 October 2004.

The latest updates and all presentations of previous workshops can be found at www.itu.int/ITU-T/worksem.

Promotion

Promoting the strengths of ITU-T will continue to receive special attention in 2004 to maintain the momentum ITU-T has built up in its promotion activities (the fruits of which could be seen, for example, in the press take-up of the 2003 Informal Forum Summit). Promotion activities are geared towards refurbishing the image of ITU-T; attracting new work areas for standardization; attracting new members; and retaining current members. In 2004, TSB has started a monthly newsletter, the “ITU-T e-flash”, reaching already a worldwide audience of several thousand (to subscribe, send “subscribe" in the subject to ITU-T_e-flash@itu.int. Previous editions are available at www.itu.int/ITU-T/e-flash.)

Regional Presence

Regional presence will continue in accordance with Resolution 25, “Strengthening the regional presence” (Rev. Marrakesh, 2002) and Resolution 123, “Bridging the standardization gap between developing and developed countries” (Marrakesh, 2002) through promotional activities in the regions, workshops and WTSA Regional Consultation Sessions.

Coordination on Domain Names and International Domain Names (IDN)

Special attention will be brought to this field according to Resolution 102 (Rev. Marrakesh, 2002) on Management of Internet domain names and addresses and Resolution 133 (Marrakesh, 2002) on the Role of administrations of Member States in the management of internationalized (multilingual) domain names.

Editing/Publishing

We continue to pre-publish all Recommendations not only within the required 4 week-delay, but to pre-publish 80% of the Recommendations within 2 weeks after the announcement of their approval in the AAP-notification.

Numbering Services

The Operational Bulletin, first published more than 35 years ago, continues to provide all administrations, operators and service providers as a favoured medium for the exchange of essential information on changes in international telecommunications networks and services.

The website on numbering issues is among the most frequented pages of ITU-T. The number of UIFNs (Universal International Freephone Numbers) is expected to stabilize at about 3000 registrations for 2004.

Operational Plan 2005

The year 2005 will be the first year of the new ITU-T study period 2005-2008. Activities and meeting schedule are subject to decisions and changes that might occur at WTSA-04. The proposed budget for 2005 is 12.596.000 CHF.

- For this draft of the Operational Plan 2005, the number of ITU-T Groups is taken to be the same as in 2004 (12 Study Groups, 1 Special Study Group and TSAG), generating about the same output as in 2004 and 2003. Details are contained in Annex 3 and Annex 4. The number of TSB-staff is assumed to be the same as in 2004.

Outlook for 2006-07

The budget forecast for 2006-2007 is very close to the budget of the 2004-05 biennium in order to achieve the limit of CHF 50,994,000 for 2004-2007 set by Decision 6 (Marrakesh, 2002). The ITU-T budget for the biennium must therefore not exceed 25.199.000 CHF.  The budget is slightly less than in 2004-2005 since there is no WTSA in the second biennium. Details are contained in Annexes 5-8.

Annex 1: Summary of TSB staff resources in 2004

Annex 2: Linkage between Strategic, Financial and Operational Planning for the Operational Plan 2004

Annex 3: Summary of TSB staff resources in 2005

Annex 4: Linkage between Strategic, Financial and Operational Planning for the Operational Plan 2005

Annex 5: Summary of TSB staff resources in 2006

Annex 6: Linkage between Strategic, Financial and Operational Planning for the Operational Plan 2006

Annex 7: Summary of TSB staff resources in 2007

Annex 8: Linkage between Strategic, Financial and Operational Planning for the Operational Plan 2007

Annex 1: Use of TSB resources in 2004 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Primary costs CHF (Draft ITU-T budget) | Document costs CHF (Draft Gen. Sec. Budget) |
| --- | --- | --- | --- | --- |
| – WTSA-04, 8 working days | 11 | 8 | 566,000 | 461,000 |
| – WTSA Regional consultation sessions | 3 | 1 | 258,000 | 64,000 |
| – TSAG (Telecommunication Standardization Advisory Group) 1 planned meeting, 5 working days | 8 | 6 | 88,000 | 79,000 |
| – Chairmen’ meetings: 1 planned meeting, 3 working days | 1 | 1 |  |  |
| – Study Group meetings: | 73 | 124 | 1,361,000 | 4,029,000 |
| 17 planned meetings, 112 working days |  |  |  |  |
| 5 post WTSA meetings, 38 working days |  |  |  |  |
| 12 Study Groups + Regional tariff groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 196 Questions under study |  |  |  |  |
| 265 new ITU-T Recommendations, |  |  |  |  |
| 11,770 pages of text |  |  |  |  |
| 13,545 pages of translation in F, E, S |  |  |  |  |
| 19,444 pages of typing pool in F, E, S |  |  |  |  |
| 11,600,000 pages of reprography |  |  |  |  |
| – Seminars and technical workshops organized by ITU-T: 12 planned workshops | 23 | 7 | 50,000 |  |
| – Regional presence: Study Group meetings in the regions Workshops in the regions | 5 | 10 | - |  |
| – Promoting ITU-T activities | 18 | 9 | 46,000 |  |
| – External cooperation | 9 | 11 |  |  |
| – Study Group publications: 12,000 pages of Recommendations to be published per language (x3) | 22 | 151 | 275,000 | 175,000 |
| – Operational Bulletin: 24 issues a year | 17 | 16 | 19,000 | 20,000 |
| – Databases accessible to public | 5 | 3 |  |  |
| – UIFN registrar (Universal International Freephone Numbers) 3,000 UIFN | 2 | 13 | 156,000 |  |
| – UIPRN/UISCN registrar (Universal International Premium Rate Numbers) (Universal International Shared Cost Numbers) 400 UIPRN/UISCN | 1 | 1 | 16,000 |  |
| – Bureau support | 32 | 19 |  | 212,000 |
| – EDH (Electronic Document Handling) Documents & information posted on ITU Website |  | 25 |  |  |
| - Cost of TSB 230 P staff-months & 405 G staff-months |  = 230 |  = 405 | 10,364,000 |  |
| – Total of allocated resources |  |  | 13,199,000 | 5,040,000 |

Assumption: 10 staff-months per person per year

##### Annex 2: ITU-T - Linkage between Strategic, Financial and Operational Planning - 2004

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2004 budget | #### Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| #### World Telecommunication | #### Expected results: |  | #### Constitution Art. 17: |
| #### Standardization Assembly |  | 1 Assembly | #### Functions and structure |
|  | #### Definition of future orientations | 8 working days |  |
|  | #### of the Sector |  | #### Constitution Art. 18: |
|  |  |  | #### World Telecommunication Standardization |
|  | #### Structure and functioning review | 11 P staff-months | #### Assemblies |
|  |  | 8 G staff-months |  |
|  | #### Achievement indicators: |  | #### Convention Art. 13: |
|  | #### Enhanced efficiency of the Sector | 566,000 F primary costs | #### World telecommunication Standardization |
|  | #### Attractive to membership | 461,000 F document costs | #### Assembly |
| #### WTSA Regional consultation sessions | #### Expected results: | 3 P staff-months | #### Resolution 25 (Rev. Marrakesh, 2002) |
|  | #### Associate regional participation | 1 G staff-month | #### Strengthening the regional presence |
|  | #### in the preparation of WTSA-04 |  |  |
|  |  | 258,000 F primary costs | #### Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 64,000 F document costs | #### Strategic Plan for the Union 2004-2007 |
|  | #### Achievement indicator: Greater presence of Regions in ITU-T activities Development of standards taking |  | #### . Goal 6, Chap. 5 WTSA Resolution 17(Montreal, 2000) Telecommunication standardization in relation to the interests of developing countries |
|  | #### into account interests of developing |  | #### Council resolution 1183 |
|  | #### countries |  | #### ITU regional presence |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2004 budget | #### Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Telecommunication Standardization Advisory Group |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: |  |  |
| Reviews progress of work program & working methods |  | 1 planned meeting | Res. 18 (WTSA-2000) |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | with its working parties | Principles and procedures for the allocation of work |
| ITU-T) |  | 5 working days | to, and coordination between, the |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations |  | Radiocommunication and Telecommunication |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 8 P staff-months | Standardization Sectors |
| Advises on financial matters |  | 6 G staff-months |  |
| cooperation and coordination | Achievement indicators: |  | Res. 22 (WTSA-2000) |
|  |  | 88,000 F primary costs: | Authorization for TSAG to act between WTSAs |
|  | Minimized duplication of work | Interpretation, |  |
|  | Harmonized technical standards | Meeting staff, | Res. 32 (WTSA-2000) |
|  | Enhanced operational efficiency |  | Strengthening the use of electronic document |
|  | of ITU-T | 79,000 F document costs : | Handling for the work of ITU-T |
|  |  | Translation, typing pool |  |
|  |  | Reprography | Res. 33 (WTSA-2000) |
|  |  | (Internal invoicing) | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 1 planned meeting |  |
| Finalization of meeting schedule for the following year |  | 3 working days |  |
| Discussion on budget allocation of the various SGs |  |  |  |
| Improvement in communication amongst SGs |  | 1 P staff-month |  |
| Priorities in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2004 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| Study Group Meetings | Expected results: | Total for all the Study Groups: |  |
| Study Group responsibility and mandates: | +/- 265 new ITU-T Recs. and other | 17 planned SG meetings | Article 17 of the Constitution |
| See Res. 2 (WTSA-2000) | texts totaling about 11,770 pages | with their working parties |  |
|  | x 3 languages | 112 working days | Article14 of the Convention |
|  |  | + 5 post WTSA SG meetings |  |
|  |  | 38 working days |  |
|  | Development of a programme of |  |  |
|  | technical workshops | 73 P staff-months | Resolutions of PP-02 (Marrakesh, 2002) |
|  |  | 124 G staff-months | See below |
| 12 Study Groups + Regional tariff groups | Key performance indicators: | 1,361,000 F primary costs: |  |
| 1 Special Study Group |  | Interpretation |  |
| 196 technical, operating and tariff Questions under study | Worldwide utilization of ITU-T Recs. | Meeting staff |  |
|  | Text quality & market response | Mail expenses |  |
| Attention is paid to improvement of telecommunications | Reduction in time-to-market for | 4,029,000 F document costs : |  |
| in developing countries and cooperation with national, | Recs (AAP implementation) | Total French +English +Spanish: |  |
| regional and international organizations | Stability of texts and avoidance of | 13,545 pages of translation |  |
|  | document reprocessing | 19,444 pages of typing pool |  |
|  | Membership satisfaction | 11,600,000 pages of reprography |  |
| Development of a Guide for Study Groups to take needs of end-users into account |  |  |  |
| Development of a Guide to help developing countries participate in ITU-T activities |  |  |  |
| Development of the 2nd edition of the “ITU-T Security Manual”, to be ready for the Cybersymposium in Florianópolis, Brazil, 4 October 2004. |  |  |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2004 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| SG 2 – Operational aspects of service provision, |  |  |  |
| networks and performance |  |  | Res. 21 (Rev. Marrakesh, 2002): Alternative calling |
|  |  |  | procedures on international telecom. networks |
| Priorities: | Expected results: | 1 planned SG meeting |  |
| Service definition, Numbering, Routing and Global Mobility |  | and its WPs | Res. 121 (Marrakesh, 2002): |
| Numbering Coordination Team (NCT) | 15 Recommendations to be | 9 working days | Review of the International Telecommunication |
| Resolution 20 and coordination with TSB | approved in 2004 = 300 pages |  | Regulations |
| Security requirements |  | 7 P staff months |  |
| ENUM |  | 5 G staff months | Res. 102 (Rev. Marrakesh, 2002): |
| Service level agreements (SLAs) |  |  | Internet Protocol (IP)-based networks |
|  |  | 59,000 F primary costs |  |
| Lead Study group for service definition, numbering |  | 131,000 F document costs | Res. 89 (Minneapolis, 1998): |
| and routing |  |  | Decreased use of international telex service |
| New activities: |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Internet domain names and addresses |  |  |  |
| Disaster relief and Mitigation Operations (Formerly ETS) |  |  | Res. 20 (WTSA-2000) : |
| Security Aspects for Networks |  |  | Procedures for allocation and management of |
|  |  |  | International numbering resources |
| Workshop |  | 2 days |  |
|  |  |  | Opinion D (WPTF-2001): |
| Spam |  |  | Essential studies by ITU to facilitate the introduction |
|  |  |  | Of “IP Telephony” |
| 9 Questions |  |  |  |
|  |  |  | Res. 130 (Marrakesh, 2002): |
|  |  |  | Strengthening the Role of ITU in Information and |
|  |  |  | Communication Network Security |
|  |  |  | Res. 131 (Marrakesh, 2002): |
|  |  |  | Community Connectivity Indicators |
|  |  |  | Res. 133 (Marrakesh, 2002): |
|  |  |  | Role of Administrations of Member States in the |
|  |  |  | Management of Internationalized (multilingual) |
|  |  |  | Domain Names |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2004 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| SG 3 - Tariff and accounting principles, including |  |  |  |
| related telecommunications, economic and |  |  |  |
| policy issues |  |  |  |
|  |  |  | Res. 71 (Rev. Marrakesh, 2002) |
| Priorities: | Expected results: | 1 planned SG meeting | Strategic Plan for the Union 2004-2007 |
| Accounting rate reform and implementation of new |  | and its WPs |  |
| remuneration systems | 5 Recommendations to be | 5 working days | Res. 21 (Rev. Marrakesh, 2002): Special measures |
| Implementation of Resolutions adopted by PP-02 (ITR) | approved in 2004: 250 pages |  | concerning alternative calling procedures on |
| Improvement and implementation of cost methodologies |  | 5 P staff months | international telecommunication networks |
| Impact of new practices bypassing accounting rate system |  | 5 G staff months |  |
| Tariff principles for services using new technologies |  | 81,000 F primary costs | Res. 22 (Minneapolis, 1998): Apportionment of |
|  |  | 90,000 F document costs | revenues in providing international telecom. services |
| New activities: |  |  |  |
| Impact and tariff study on Internet / IP-based Networks |  |  | Res. 101 (Minneapolis, 1998): |
| New Generation Network |  | 2 Rapporteur meetings | Internet Protocol (IP)-based networks |
| Settlement of balance of account based on IP Detailed |  | 5 working days |  |
| Records |  |  | Res. 79 (Minneapolis, 1998): |
| Tariff principles for international mobile services |  |  | International Telecommunication Regulations |
| Impact of Network externalities |  |  |  |
| 4 Questions |  |  | Res. 121 (Marrakesh, 2002): |
|  |  |  | Review of the International Telecommunication |
| Tariff Group for Africa (TAF) |  |  | Regulations |
| Tariff Group for Latin America (TAL) |  |  |  |
| Tariff Group for Asia and Oceania (TAS) |  |  |  |
| Priorities: |  |  | Res. 26 (WTSA-2000) |
| TAF: Accounting rates, Call back, Cost model development | Expected results: | 3 planned meetings | Assistance to the Regional Tariff Groups |
| TAL: Cost model development (Interconnection) |  | 10 working days |  |
| Determination of maximum accounting rates | Preparation of Recommendations |  | Res. 29 (WTSA-2000) |
| TAS: New cost model development, | and regional cost model | 3 P staff months | Alternative calling procedures on international |
| Regional case study on cost/price |  | 3 G staff months | telecommunication networks |
| Regional tariff model for Internet |  |  |  |
| 1 Workshop on tariff principles and methodologies in TAF region |  | 3 days |  |
| 1 Workshop same topics in TAL region and TAS region |  | 3 days | Res. 41 (WTSA-2000) |
|  |  |  | Accounting rate principles for international |
| New activities: |  |  | telephone services |
| TAF: Use of internet in Africa |  |  |  |
| TAL: Impact of IP Telephony in the region |  |  |  |
| TAS, TAF, TAL: Review of ITR |  |  |  |
| Tariff Group for Europe and the Mediterranean Basin |  |  |  |
| activity in abeyance |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 4 – Telecommunication management, |  |  |  |
| including TMN |  |  |  |
| Priorities: | Expected results : | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| TMN principles and architecture | 20 Recommendations to be | and its WPs | Strategic Plan for the Union 2004-2007 |
| - consolidation of functional requirements and | approved in 2004: 1,200 pages | 10 working days |  |
| business approaches |  |  |  |
|  |  | 8 P staff months |  |
| TMN infrastructure |  | 8 G staff months |  |
| - common working methods for specifying requirements |  |  |  |
| and modelling |  | 42,000 F primary costs |  |
| - protocols |  | 172,000 F document costs |  |
| - open distributed management |  |  |  |
| - IP-based TMN framework |  |  |  |
| - extension of telecommunication Markup Language(tML) |  |  |  |
| to ASN.1, UML, and intra TMN (Q) interfaces |  |  |  |
| Support for inter-TMN (X) interfaces |  |  |  |
| - application of tML framework |  |  |  |
| - Global Telecommunication Data Dictionary |  |  |  |
| - management of emergency telecommunication service |  |  |  |
| - QoS/SLA management |  |  |  |
| Application of CORBA-based TMN framework |  |  |  |
| Integrated management of hybrid circuit/packet/IP |  |  |  |
| networks |  |  |  |
| TMN information modelling |  |  |  |
| - support of IEEE 802.3 based transport network management |  |  |  |
| TMN support for 3G wireless |  |  |  |
| Performance objectives and procedures, test equipment, |  |  |  |
| and inter-operator designations |  |  |  |
| - restructuring of Recommendation M.1400 |  |  |  |
| Recommendation M.1400 layer 1 extension |  |  |  |
| Cooperation with outside SDOs, forums and consortia |  |  |  |
| New activity: management on NGN |  |  |  |
| Lead Study Group on TMN |  |  |  |
| 17 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 5 - Protection against electromagnetic |  |  |  |
| environment effects |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Resistibility, EMC and safety aspects related to |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| telecommunications networks | 14 Recommendations to be | 5 working days |  |
| Cooperation with other international organizations | approved in 2004: 200 pages |  |  |
|  |  | + 1 post WTSA SG meeting |  |
| New activity: | 1 handbook, 50 pages | 5 working days |  |
| Protection against the effects of mobile equipment and |  |  |  |
| radio systems |  | 3 P staff months |  |
| Unbundling and interoperability in telecom networks |  | 3 G staff months |  |
|  |  | 43,000 F primary costs |  |
|  |  | 62,000 F document costs |  |
| 14 Questions |  |  |  |
| SG 6 - Outside plant |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Outside plant and access for telecommunication |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| networks, bundling, access for multiservices/multioperators | 11 Recommendations to be | 5 working days |  |
|  | approved in 2004 = 400 pages |  |  |
| Cooperation with IEC, especially TC 86, TC 46 and SB4 |  | 2 P staff months |  |
|  | 1 handbook to be revised: | 2 G staff months |  |
| 10 Questions | 100 pages | 27,000 F primary costs |  |
|  |  | 62,000 F document costs |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| ###### SG 9 – Integrated broadband cable networks and |  |  |  |
| television and sound transmission |  |  |  |
| Priorities: | Expected results: | 2 planned SG meetings: | Res. 71 (Rev. Marrakesh, 2002) |
| IP and GII over cable distribution networks |  | 10 working days | Strategic Plan for the Union 2004-2007 |
| Emergency Telecommunications on the IPCablecom | 20 Recommendations to be |  |  |
| architecture | approved in 2004: 2,000 pages |  | Res. 101 (Minneapolis, 1998): |
| IPCablecom for enhanced Multimedia capabilities |  | 6 P staff months | Internet Protocol (IP)-based networks |
|  |  | 9 G staff months |  |
| Television and sound over the core network |  | 115,000 F primary costs |  |
|  |  | 631,000 F document costs |  |
| Lead Study Group on integrated broadband cable |  |  |  |
| and television networks |  |  |  |
| Large Screen Digital Imagery |  |  |  |
| Coordination with ITU-R SG 6 on broadcasting matters |  |  |  |
| Webcasting |  |  |  |
| Packet cable, IP over cable |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 11 - Signalling requirements and protocols |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| Signalling support for Internet (IP)-based applications | 25 Recommendations to be | 10 working days |  |
|  | approved in 2004, 1200 pages |  |  |
| Intelligent Networks. |  | + 1 post WTSA SG meeting |  |
|  |  | 10 working days |  |
| Lead Study Group on intelligent networks |  |  |  |
| Signalling for Access, N&B-ISDN, |  | 7 P staff months |  |
| and new generation networks |  | 7 G staff months |  |
|  |  | 151,000 F primary costs |  |
| Cooperation and development of ITU-T Recommendations |  | 723,000 F document costs |  |
| with regional standards bodies/fora on signalling-related |  |  |  |
| activities for IP |  |  |  |
|  |  | 16 Rapporteur meetings |  |
| Coordination with relevant ITU-T/ITU-R SGs/Wps for |  | of 4 days each |  |
| signaling support of fixed-mobile aspects |  |  |  |
| New activities: |  |  |  |
| - Signalling for New Generation Networks (NGN) |  |  |  |
| - SIP – profiles |  |  |  |
| - Signalling protocols for ATM over MPLS |  |  |  |
| 1 workshop |  | 2 days |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 12 - End-to-end transmission performance of |  |  |  |
| networks and terminals |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Performance assessment |  | and its WPs | Strategic Plan for the Union 2004-2007 |
|  | 14 Recommendations to be | 7 working days |  |
| Lead Study Group on Quality of services and performance | approved in 2004: 150 pages |  | Res. 101 (Minneapolis, 1998): |
|  |  | 5 P staff months | Performance quality assessment of IP-based networks |
| New activities: |  | 6 G staff months |  |
| Development of Recs. on Quality aspects of IP-based | 1 Handbook (70 pages) | 31,000 F primary costs |  |
| network |  | 90,000 F document costs |  |
|  |  | 1 WP meeting, 5 days |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 13 – Multi-protocol and IP-based networks |  |  |  |
| and their internetworking |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 73 (Minneapolis, 1998): |
| General network aspects, Global Information |  | and its WPs | World Summit on the information society |
| Infrastructures (GII, NGN), B-ISDN and IP | 24 Recommendations to be | 9 working days |  |
| Fostering cooperation with IETF | approved in 2004: 1,000 pages |  | Res. 101 (Minneapolis, 1998): |
|  |  | + 1 post WTSA SG meeting | Internet Protocol (IP)-based networks |
| Monitoring IP and NGN 2004 projects |  | 9 working days |  |
|  |  |  | Res. 71 (Rev. Marrakesh, 2002) |
| Lead Study Group for IP related matters, B-ISDN, |  | 4 P staff months | Strategic Plan for the Union 2004-2007 |
| Global Information Infrastructure and satellite matters |  | 8 G staff months |  |
|  |  | 82,000 F primary costs | Res. 130 (Marrakesh, 2002) |
|  |  | 216,000 F document costs | Strengthening the role of ITU in information and |
| NGN |  |  | communication network security |
| MPLS interworking |  | 5 Rapporteurs meetings |  |
| VPN (Virtual Private Network) |  | of 5 days each |  |
| Integrated communication architecture, including the |  |  |  |
| impact of convergence |  |  |  |
| Interworking |  |  |  |
| Performance |  |  |  |
| New activity; Joint Rapporteur Group (JRG) on NGN |  |  |  |
| 15 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| ICG SAT |  |  |  |
| Intersector Coordination Group on Satellite Matters |  |  |  |
| Under the Lead of SG 13 |  |  |  |
| Priorities: | Expected results: | 1 planned ICG-SAT meeting | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 3 working days | Strategic Plan for the Union 2004-2007 |
| To take into account satellite specificity within | Performance |  |  |
| telecommunication network including impact of | Achieved consistency of |  |  |
| IP-based network and multimedia network and system | Recommendations of various |  |  |
| Keeping up to date database | Study Groups for full integration |  |  |
|  | of the sat-transmission in |  |  |
| Coordination with ITU-R | public networks |  |  |
| The organization of a workshop will be considered |  |  |  |
| Strengthening relationship with ITU-D |  |  |  |
| SG 15 – Optical and other transport networks |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Access Network | 35 Recommendations to be | and its WPs | Strategic Plan for the Union 2004-2007 |
| - broadband optical access, Multigigabit PONS | approved in 2004: 1,800 pages | 10 working days |  |
| - refinement & enhancement to SDL |  |  |  |
| - IP on Access Network |  | 6 P staff months |  |
| Network signal processing |  | 7 G staff months |  |
| - interaction of signal processing (OTN) |  | 123,000 F primary costs |  |
| Optical transport network structure |  | 831,000 F document costs |  |
| - automatic switched optical network (ASON) |  |  |  |
| - network management & control |  |  |  |
| OTN Technology |  |  |  |
| - coarse & dense wavelength division multiplexing (WDM) |  |  |  |
| - fiber characteristics |  |  |  |
| - transmission technology |  |  |  |
| - IP on WDM |  |  |  |
| Cooperation with IEC and other SDOs |  |  |  |
| Lead Study Group on access network transport |  |  |  |
| Lead Study Group on optical technology |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 16 - Multimedia services, systems and |  |  |  |
| terminals |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Multimedia communications and interworking |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| (including IP and NGN) | 60 Recommendations to be | 9 working days |  |
| Security for Multimedia systems | approved in 2004: 1,500 pages |  | Res. 101 (Minneapolis, 1998): |
| Media Coding |  | + 1 post WTSA SG meeting | Internet Protocol (IP)-based networks |
| Multimedia framework, MEDIACOM-2004 project |  | 9 working days |  |
| Telecommunications for Disaster Relief (TDR) |  |  |  |
| Accessibility for people with disabilities |  | 8 P staff months |  |
|  |  | 8 G staff months |  |
| Cooperation with other Standard Development |  | 151,000 F primary costs |  |
| Organization |  | 624,000 F document costs |  |
| Lead Study Group on multimedia services, |  |  |  |
| systems and terminals |  | 4 Rapporteur meetings |  |
| Lead Study Group on e-business and e-commerce |  | 1 week each |  |
| New activities: |  |  |  |
| E-commerce, E-business |  |  |  |
| E-health |  |  |  |
| 2 workshops |  | 3 days each |  |
| 23 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 17 - Data Networks and Telecommunication |  |  |  |
| Software |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Communication System Security |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| Development of a new OID database | 20 Recommendations to be | 8 working days |  |
| Addition to a set of Directory Recommendations | approved in 2004: 1,500 pages |  | Res. 130 (Marrakesh, 2002) |
| Complement to the set of ASN.1 Recommendations |  | 4 P staff months | Strengthening the role of ITU in information and |
| Language coordination and promotion |  | 10 G staff months | communication network security |
| Cooperation with ISO/IEC |  |  |  |
| Contribution to the coordination effort with ISO, IEC and |  | 49,000 F primary costs | Res. 101 (Minneapolis, 1998) |
| UN/ECE for E-business standardization |  | 222,000 F document costs | Collaborative activities on IP-based network with |
| Open Distributed Processing (ODP), Frame Relay |  |  | ISOC/IETF |
| Development of Framework Recommendations on Security |  |  |  |
|  |  |  | TSAG (Geneva, 19-23 March 2001) |
| Lead Study Group on Frame Relay |  |  | TSAG approved the merger of Study group 7 and 10 |
| Lead Study Group on Communication System Security |  |  | into a single Study Group 17 |
| Lead Study Group on Languages and Description |  | 15 Rapporteur meetings |  |
| Techniques |  | of 1 to 5 days each |  |
| Further development of the ITU-T ASN.1 Project |  |  |  |
| Continuation of the provision of ASN.1 modules to the |  |  |  |
| ASN.1 database |  |  |  |
| Further development of the ITU-T language coordination |  |  |  |
| project |  |  |  |
| Further development of the ITU-T Security project |  |  |  |
| 2 workshops |  | 3 days |  |
| 27 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SSG – Special Study Group IMT-2000 and beyond |  |  |  |
|  |  |  | Res. 38 (WTSA-2000) |
| Priorities: |  |  | Coordination among ITU-T, ITU-R and ITU-D for |
| Network aspects of IMT-2000 and beyond | Expected results: | 1 proposed SSG meeting | IMT-2000 activities |
| (International Mobile Telecommunications-2000) |  | 5 working days |  |
| Wireless access to IP-based networks |  |  |  |
| Convergence of mobile and fixed networks |  | + 1 post WTSA SSG meeting |  |
| Mobility management, mobile multimedia functions | 2 Recommendations to be | 5 working days |  |
| Internetworking, interoperability and harmonization | approved in 2004: 270 pages |  |  |
| between IMT-2000 systems |  | 7 P staff months |  |
| Network vision of systems beyond IMT-2000 | 5 Technical Reports to be | 8 G staff months |  |
|  | approved in 2004: 140 pages | 36,000 F primary costs |  |
| Enhancement of ITU-T Recommendations on IMT-2000 |  | 175,000 F document costs |  |
| Lead Study Group on IMT-2000 and beyond | Amendment to Handbook on | 2 Rapporteur meetings |  |
| and for mobility | IMT-2000 to be approved in 2004: | 7 working days |  |
|  | 30 pages |  |  |
| New activities: |  | 1 Editor’s meeting |  |
|  |  | 2 working days |  |
| Workshop on IMT-2000 Core Networks |  |  |  |
| Electronic meetings, electronic drafting groups |  | 4 electronic meetings |  |
|  |  | 40 days |  |
| 7 Questions |  | 1 workshop, 1 day |  |
| Workshops |  |  |  |
|  | Expected results: | 23 P staff-months | Resolution 71 (Rev. Marrakesh, 2002): |
| Dissemination of expert knowledge on state-of-the-art |  | 7 G staff-months | Goal 3, 5, 6, Chapter 5 |
| technologies, | New study topics for Study Groups |  |  |
|  | Participation of delegates from | 50,000 F primary costs: | Resolution 25 (Rev. Marrakesh, 2002) |
| Promotion of awareness of ITU-T activities, | developing countries in the | Fellowships for SG 3 | Strengthening the regional presence |
| working methods and priorities | activities of the Sector |  |  |
|  |  |  | WTSA Resolution 17 (Montreal, 2000) |
| Exploring new study topics | Strengthening regional presence |  | telecommunication standardization in relation |
|  |  |  | to the interests of developing countries |
|  | Achievement indicators: |  |  |
|  | Dissemination of expert technology |  |  |
|  |  |  | Council Resolution 1181 |
|  | Integration of developing countries |  | Recommendations on ITU Reform, WGR R7 |
|  | concerns in ITU-T outputs |  |  |
|  | Coordination of activities within |  | Council Resolution 1183 |
|  | Study Groups and with other SDOs |  | ITU regional presence |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Regional presence |  |  | Resolution 25 (Rev. Marrakesh, 2002) |
|  |  |  | Strengthening the regional presence |
| Strengthening the regional presence | Expected results: | SG meetings in the regions | “regional meetings should be organized in the various |
| Participation in external conferences |  | Workshops in the regions | regions by the relevant Sectors, particularly ITU-D, in |
| Assistance to ITU-D | Strengthened regional presence |  | order to improve the participation in and effectiveness |
|  | Awareness of ITU-T activities |  | of the corresponding global meetings” |
|  |  | 5 P staff-months | Resolution 123 (Marrakesh, 2002) |
|  |  | 10 G staff-month | Bridging the standardization gap between developing |
|  |  |  | and developed countries |
|  | Achievement indicators: |  | WTSA Resolution 17 (Montreal, 2000) |
| Organization of seminars in the field |  |  | telecommunication standardization in relation |
| Assistance to the Regions | Membership satisfaction |  | to the interests of developing countries |
|  | Dissemination of ITU-T studies |  |  |
|  | and Recommendations |  | Council Resolution 1183 |
|  |  |  | ITU regional presence |
|  |  |  | Resolution 71 (Rev. Marrakesh, 2002): |
| Promoting ITU-T |  |  | Goal 3, 5, 6, Chapter 5 |
|  | Expected results: | 18 P staff-months | “to develop and execute a proactive plan, in |
| Press releases | Awareness of ITU-T activities | 9 G staff-month | collaboration with the secretariat, in order to promote |
| ITU-T presence in external events | Increased interest of Membership |  | the value of ITU-T in the face of competition from |
| Presentation of ITU-T activities during |  | 46,000 F primary costs | other standards bodies and to continue to enhance |
| external workshops | Achievement indicators: |  | efforts in this regards” |
| Promotion events | Higher number of Sector Members |  |  |
| Articles | Increased participation in the |  | Council Resolution 1181 |
| Promotional material | Sector activities |  | Recommendations on ITU Reform, WGR R7 |
| Website promotional content |  |  | “Recognizing the need to improve awareness of |
|  |  |  | ITU-T products and services, and the image of the |
|  |  |  | Union in general, Council instructs the Secretary- |
|  |  |  | General and the Director of the TSB to define and |
|  |  |  | implement a corresponding promotion strategy |
|  |  |  | and to allocate appropriate resources in the budget |
| External cooperation | Expected results: |  |  |
|  | Worldwide coordination | 9 P staff-months |  |
| Assistance to membership and Telecom community | Promotion of ITU-T activities | 11 G staff-months |  |
| Assistance and cooperation with other Sectors | Signature of MoUs |  |  |
| Liaison and coordination with international and regional | Achievement indicators: |  |  |
| organizations | Customer and membership |  |  |
| SDO cooperation | satisfaction |  |  |
| Participation in external conferences | Dissemination of ITU-T studies |  |  |
| IPR issues | and Recommendations |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts in F, E, S | Expected results: | 22 P staff-months |  |
|  |  | 151 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks in |  |  |
| one month of approval. | three languages | 275,000 F primary costs | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 175,000 F invoiced costs | Strategic Plan for the Union 2004-2007 |
| Quickpub procedures | Key indicators: |  |  |
|  |  | Covered by sales revenues |  |
| Quality control of texts | Decrease time to edit publications |  |  |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 17 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 19,000 F primary costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: |  |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 2 P staff-months |  |
|  | 3,000 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 156,000 F primary costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-months | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 400 UIPRN/UISCN reservations | 1 G staff-months | Cost recovery for some products and services |
|  | Achievement indicators: | 16,000 F primary costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2004 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |
| Bureau support |  |  |  |
| Membership |  | 32 P staff-months | Res. 72 (Rev. Marrakesh, 2002): Linking strategic, |
| Meeting organization and logistical support |  | 19 G staff-months | financial and operational planning in ITU |
| Document control |  |  |  |
| Administrative support |  |  | Res. 104 (Minneapolis, 1998): |
| Finance and budget |  | 10,364,000 F primary costs | Reduction of the volume and cost of documentation |
| Director Office |  | 212,000 F document costs | for ITU conferences |
| Internal management |  |  |  |
| Operational planning |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Gender perspective issues |  |  | Res. 70 (Rev. Marrakesh, 2002): |
|  |  |  | Gender mainstreaming in ITU |
| ###### Director’s Ad Hoc IPR Group |  | 1 planned meeting | Res. 1187 Council 2001 |
|  |  | 2 days | Gender perspective in ITU Human Resource |
|  |  |  | management policy and practice |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: |  |  |
| WEB development | Immediate posting of information | 25 G staff-months | Res. 1141 Council 1999 |
| Customer support (TSB helpdesk) |  |  | Reduction of the cost and volume of documentation for |
| Alternate Approval Process Implementation | Achievement indicators: |  | Conferences and Assemblies and the Council |
|  | Increased number of visitors |  |  |
|  | Customer satisfaction |  | Res. 32 (WTSA-2000) |
| Maintaining of the ITU-T Website and relevant information |  |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

- ___________________

Annex 3: Use of TSB resources in 2005 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Primary costs CHF (Draft ITU-T Budget) | Document costs CHF (Draft Gen. Sec. Budget) |
| --- | --- | --- | --- | --- |
| – TSAG (Telecommunication Standardization Advisory Group) 2 planned meetings, 10 working days | 13 | 8 | 176,000 | 130,000 |
| – Chairmen’ meetings: 2 planned meetings, 4 working days | 1 | 1 |  |  |
| – Study Group meetings: | 77 | 130 | 1,385,000 | 8,535,000 |
| 22 planned meetings, 153 working days |  |  |  |  |
| 12 Study Groups + Regional tariff groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 196 Questions under study |  |  |  |  |
| 246 new ITU-T Recommendations, |  |  |  |  |
| 13,480 pages of text |  |  |  |  |
| 13,546 pages of translation in F, E, S |  |  |  |  |
| 19,239 pages of translation in A, C, R |  |  |  |  |
| 19,444 pages of typing pool in F, E, S |  |  |  |  |
| 25,032 pages of typing pool in A, C, R |  |  |  |  |
| 12,000,000 pages of reprography |  |  |  |  |
| – Seminars and technical workshops: 12 planned workshops | 25 | 7 | 50,000 |  |
| – Regional presence: 4 regional briefing meetings Study Group meetings in the regions Workshops in the regions | 8 | 11 | 84,000 |  |
| – Promoting ITU-T activities | 18 | 9 | 46,000 |  |
| – External cooperation | 9 | 11 |  |  |
| – Study Group publications: 12,000 pages of Recommendations to be published per language | 22 | 151 | 290,000 | 183,000 |
| – Operational Bulletin: 24 issues a year | 17 | 16 | 19,000 | 20,000 |
| – Databases accessible to public | 5 | 3 |  |  |
| – UIFN registrar (Universal International Freephone Numbers) 3,000 UIFN | 2 | 13 | 156,000 |  |
| – UIPRN/UISCN registrar (Universal International Premium Rate Numbers) (Universal International Shared Cost Numbers) 400 UIPRN/UISCN | 1 | 1 | 16,000 |  |
| – Bureau support | 32 | 19 |  | 349,000 |
| – EDH (Electronic Document Handling) Documents & information posted on ITU Website |  | 25 |  |  |
| - Cost of TSB 230 P staff-months & 405 G staff-months |  = 230 |  = 405 | 10,374,000 |  |
| – Total of allocated resources |  |  | 12,596,000 | 9,217,000 |

Assumption: 10 staff-months per person per year

##### Annex 4: ITU-T - Linkage between Strategic, Financial and Operational Planning - 2005

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2005 budget | #### Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Telecommunication Standardization Advisory Group |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: |  |  |
| Reviews progress of work program & working methods |  | 2 planned meetings | Res. 18 (WTSA-2000) |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | with their working parties | Principles and procedures for the allocation of work |
| ITU-T) |  | 10 working days | to, and coordination between, the |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations |  | Radiocommunication and Telecommunication |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 13 P staff-months | Standardization Sectors |
| Advises on financial matters |  | 8 G staff-months |  |
| cooperation and coordination | Achievement indicators: |  | Res. 22 (WTSA-2000) |
|  |  | 176,000 F primary costs: | Authorization for TSAG to act between WTSAs |
|  | Minimized duplication of work | Interpretation, |  |
|  | Harmonized technical standards | Meeting staff | Res. 32 (WTSA-2000) |
|  | Enhanced operational efficiency |  | Strengthening the use of electronic document |
|  | of ITU-T | 130,000 F document costs : | Handling for the work of ITU-T |
|  |  | Translation, typing pool |  |
|  |  | Reprography | Res. 33 (WTSA-2000) |
|  |  | (Internal invoicing) | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 2 planned meetings |  |
| Finalization of meeting schedule for following year |  | 4 working days |  |
| Discussion on budget allocation on the various SG |  |  |  |
| Improvement in communication amongst SG |  | 1 P staff-month |  |
| Priority in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2005 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| Study Group Meetings | Expected results: | Total for all the Study Groups: |  |
| Study Group responsibility and mandates: | +/- 246 new ITU-T Recs. and other | 22 planned SG meetings | Article 17 of the Constitution |
| See Res. 2 (WTSA-2000) | texts totaling about 13,480 pages | with their working parties |  |
|  | published in 6 languages | 153 working days | Article14 of the Convention |
|  | Development of a programme of |  |  |
|  | technical workshops | 77 P staff-months | Resolutions of Marrakesh, 2002 |
|  |  | 130 G staff-months | See below |
| 12 Study Groups + Regional tariff groups | Key performance indicators: | 1,385,000 F primary costs: |  |
| 1 Special Study Group |  | Interpretation |  |
| 196 technical, operating and tariff Questions under study | Worldwide utilization of ITU-T Recs. | Meeting staff |  |
|  | Text quality & market response | Mail expenses |  |
| Attention is paid to improvement of telecommunications | Reduction in time-to-market for | 8,535,000 F document costs |  |
| in developing countries and cooperation with national, | Recs (AAP implementation) | Total 6 languages: |  |
| regional and international organizations | Stability of texts and avoidance of | 32,785 pages of translation |  |
|  | document reprocessing | 44,476 pages of typing pool |  |
|  | Membership satisfaction | 12,000,000 pages of reprography |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2005 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| SG 2 – Operational aspects of service provision, |  |  |  |
| networks and performance |  |  | Res. 21 (Rev. Marrakesh, 2002): Alternative calling |
|  |  |  | procedures on international telecom. networks |
| Priorities: | Expected results: | 1 planned SG meeting |  |
| Service definition, Numbering, Routing and Global Mobility |  | and its WPs | Res. 121 (Marrakesh, 2002): |
| Numbering Coordination Team (NCT) | 15 Recommendations to be | 9 working days | Review of the International Telecommunication |
| Resolution 20 and coordination with TSB | approved in 2005 = 300 pages |  | Regulations |
| Security requirements |  | 7 P staff months |  |
| ENUM |  | 5 G staff months | Res. 102 (Rev. Marrakesh, 2002): |
| Service level agreements (SLAs) |  |  | Internet Protocol (IP)-based networks |
|  |  | 59,000 F primary costs |  |
| Lead Study group for service definition, numbering |  | 274,000 F document costs | Res. 89 (Minneapolis, 1998): |
| and routing |  |  | Decreased use of international telex service |
| New activities: |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Internet domain names and addresses |  |  |  |
| Disaster relief and Mitigation Operations (Formerly ETS) |  |  | Res. 20 (WTSA-2000) : |
| Security Aspects for Networks |  |  | Procedures for allocation and management of |
|  |  |  | International numbering resources |
| Workshop |  | 2 days |  |
|  |  |  | Opinion D (WPTF-2001): |
| Spam |  |  | Essential studies by ITU to facilitate the introduction |
|  |  |  | Of “IP Telephony” |
| 9 Questions |  |  |  |
|  |  |  | Res. 130 (Marrakesh, 2002): |
|  |  |  | Strengthening the Role of ITU in Information and |
|  |  |  | Communication Network Security |
|  |  |  | Res. 131 (Marrakesh, 2002): |
|  |  |  | Community Connectivity Indicators |
|  |  |  | Res. 133 (Marrakesh, 2002): |
|  |  |  | Role of Administrations of Member States in the |
|  |  |  | Management of Internationalized (multilingual) |
|  |  |  | Domain Names |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2005 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| SG 3 - Tariff and accounting principles, including |  |  |  |
| related telecommunications, economic and |  |  |  |
| policy issues |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Priorities: | Expected results: | 2 planned SG meetings |  |
| Accounting rate reform and implementation of new |  | and their WPs | Res. 21 (Rev. Marrakesh, 2002): Special measures |
| remuneration systems | 5 Recommendations to be | 10 working days | concerning alternative calling procedures on |
| Implementation of Resolutions adopted by PP-02 (ITR) | approved in 2005: 250 pages |  | international telecommunication networks |
| Improvement and implementation of cost methodologies |  | 5 P staff months |  |
| Impact of new practices bypassing accounting rate system |  | 5 G staff months | Res. 22 (Minneapolis, 1998): Apportionment of |
| Tariff principles for services using new technologies |  | 156,000 F primary costs | revenues in providing international telecom. services |
|  |  | 384,000 F document costs |  |
| New activities: |  |  | Res. 101 (Minneapolis, 1998): |
| Impact and tariff study on Internet / IP-based Networks |  |  | Internet Protocol (IP)-based networks |
| New Generation Network |  | 2 Rapporteur meetings |  |
| Settlement of balance of account based on IP Detailed |  | 5 working days | Res. 79 (Minneapolis, 1998): |
| Records |  |  | International Telecommunication Regulations |
| Tariff principles for international mobile services |  |  |  |
| 4 Questions |  |  | Res. 121 (Marrakesh, 2002): |
|  |  |  | Review of the International Telecommunication |
| Tariff Group for Africa (TAF) |  |  | Regulations |
| Tariff Group for Latin America (TAL) |  |  |  |
| Tariff Group for Asia and Oceania (TAS) |  |  |  |
| Priorities: |  |  | Res. 26 (WTSA-2000) |
| TAF: Accounting rates, Call back, Cost model development | Expected results: | 3 planned meetings | Assistance to the Regional Tariff Groups |
| TAL: Cost model development |  | 10 working days |  |
| Determination of maximum accounting rates | Preparation of Recommendations |  | Res. 29 (WTSA-2000) |
| TAS: New cost model development, | and regional cost model | 3 P staff months | Alternative calling procedures on international |
| Regional case study on cost/price |  | 3 G staff months | telecommunication networks |
| Regional tariff model for Internet |  |  |  |
| 1 Workshop on tariff principles and methodologies in TAF region |  | 3 days |  |
| 1 Workshop same topics in TAL region and TAS region |  | 3 days | Res. 41 (WTSA-2000) |
|  |  |  | Accounting rate principles for international |
| New activities: |  |  | telephone services |
| TAF: Use of internet in Africa |  |  |  |
| TAL: Impact of IP Telephony in the region |  |  |  |
| TAS, TAF, TAL: Review of ITR |  |  |  |
| Tariff Group for Europe and the Mediterranean Basin |  |  |  |
| activity in abeyance |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 4 – Telecommunication management, |  |  |  |
| including TMN |  |  |  |
| Priorities: | Expected results : | 2 planned SG meetings | Res. 71 (Rev. Marrakesh, 2002) |
| TMN principles and architecture | 30 Recommendations to be | and their WPs | Strategic Plan for the Union 2004-2007 |
| - consolidation of functional requirements and | approved in 2005: 1,200 pages | 20 working days |  |
| business approaches |  |  |  |
|  |  | 8 P staff months |  |
| TMN infrastructure |  | 8 G staff months |  |
| - common working methods for specifying requirements |  |  |  |
| and modelling |  | 79,000 F primary costs |  |
| - protocols |  | 640,000 F document costs |  |
| - open distributed management |  |  |  |
| - IP-based TMN framework |  |  |  |
| - extension of telecommunication Markup Language(tML) |  |  |  |
| to ASN.1, UML, and intra TMN (Q) interfaces |  |  |  |
| Support for inter-TMN (X) interfaces |  |  |  |
| - application of tML framework |  |  |  |
| - Global Telecommunication Data Dictionary |  |  |  |
| - management of emergency telecommunication service |  |  |  |
| - QoS/SLA management |  |  |  |
| Application of CORBA-based TMN framework |  |  |  |
| Integrated management of hybrid circuit/packet/IP |  |  |  |
| networks |  |  |  |
| TMN information modelling |  |  |  |
| - support of IEEE 802.3 based transport network management |  |  |  |
| TMN support for 3G wireless |  |  |  |
| Performance objectives and procedures, test equipment, |  |  |  |
| and inter-operator designations |  |  |  |
| - restructuring of Recommendation M.1400 |  |  |  |
| Recommendation M.1400 layer 1 extension |  |  |  |
| Management on NGN |  |  |  |
| Cooperation with outside SDOs, forums and consortia |  |  |  |
| Lead Study Group on TMN |  |  |  |
| 17 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 5 - Protection against electromagnetic |  |  |  |
| environment effects |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Resistibility, EMC and safety aspects related to |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| telecommunications networks | 7 Recommendations to be | 5 working days |  |
| Cooperation with other international organizations | approved in 2005: 200 pages |  |  |
|  |  | 3 P staff months |  |
| New activity: | 1 handbook, 50 pages | 3 G staff months |  |
| Protection against the effects of mobile equipment and |  | 28,000 F primary costs |  |
| radio systems |  | 133,000 F document costs |  |
| Unbundling and interoperability in telecom networks |  |  |  |
| 14 Questions |  |  |  |
| SG 6 - Outside plant |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Outside plant and access for telecommunication |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| networks, bundling, access for multiservices/multioperators | 14 Recommendations to be | 5 working days |  |
|  | approved in 2005 = 500 pages |  |  |
| Cooperation with IEC, especially TC 86, TC 46 and SB4 |  | 2 P staff months |  |
|  |  | 2 G staff months |  |
| 10 Questions |  | 26,000 F primary costs |  |
|  |  | 133,000 F document costs |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| ###### SG 9 – Integrated broadband cable networks and |  |  |  |
| television and sound transmission |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 71 (Rev. Marrakesh, 2002) |
| IP and GII over cable distribution networks |  | 5 working days | Strategic Plan for the Union 2004-2007 |
| Emergency Telecommunications on the IPCablecom | 20 Recommendations to be |  |  |
| architecture | approved in 2005: 2,000 pages |  | Res. 101 (Minneapolis, 1998): |
| IPCablecom for enhanced Multimedia capabilities |  | 6 P staff months | Internet Protocol (IP)-based networks |
|  |  | 9 G staff months |  |
| Television and sound over the core network |  | 71,000 F primary costs |  |
|  |  | 790,000 F document costs |  |
| Lead Study Group on integrated broadband cable |  |  |  |
| and television networks |  |  |  |
| Large Screen Digital Imagery |  |  |  |
| Coordination with ITU-R SG 6 on broadcasting matters |  |  |  |
| Webcasting |  |  |  |
| Packet cable, IP over cable |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 11 - Signalling requirements and protocols |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| Signalling support for Internet (IP)-based applications | 25 Recommendations to be | 10 working days |  |
|  | approved in 2005, 1200 pages |  |  |
| Intelligent Networks. |  | 7 P staff months |  |
|  |  | 7 G staff months |  |
| Lead Study Group on intelligent networks |  | 87,000 F primary costs |  |
|  |  | 847,000 F document costs |  |
| Signalling for Access, N&B-ISDN, |  |  |  |
| and new generation networks |  |  |  |
|  |  | 8 Rapporteur meetings |  |
| Cooperation and development of ITU-T Recommendations |  | of 4 days each |  |
| with regional standards bodies/fora on signalling-related |  |  |  |
| activities for IP |  |  |  |
| Coordination with relevant ITU-T/ITU-R SGs/Wps for |  |  |  |
| signaling support of fixed-mobile aspects |  |  |  |
| New activities: |  |  |  |
| - Signalling for New Generation Networks (NGN) |  |  |  |
| - SIP – profiles |  |  |  |
| - Signalling protocols for ATM over MPLS |  |  |  |
| 1 workshop |  | 2 days |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 12 - End-to-end transmission performance of |  |  |  |
| networks and terminals |  |  |  |
|  |  |  | Res. 71 (Rev. Marrakesh, 2002) |
| Priorities: | Expected results: | 2 planned SG meetings | Strategic Plan for the Union 2004-2007 |
| Performance assessment |  | and their WPs |  |
|  | 10 Recommendations to be | 13 working days | Res. 101 (Minneapolis, 1998): |
| Lead Study Group on Quality of services and performance | approved in 2005: 150 pages |  | Performance quality assessment of IP-based networks |
|  |  | 5 P staff months |  |
| New activities: |  | 6 G staff months |  |
| Development of Recs. on Quality aspects of IP-based |  | 47,000 F primary costs |  |
| network |  | 384,000 F document costs |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 13 – Multi-protocol and IP-based networks |  |  |  |
| and their internetworking |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 73 (Minneapolis, 1998): |
| General network aspects, Global Information |  | and its WPs | World Summit on the information society |
| Infrastructures (GII, NGN), B-ISDN and IP | 24 Recommendations to be | 9 working days |  |
| Fostering cooperation with IETF | approved in 2005: 1,000 pages |  | Res. 101 (Minneapolis, 1998): |
|  |  | 4 P staff months | Internet Protocol (IP)-based networks |
| Monitoring IP and NGN 2004 projects |  | 8 G staff months |  |
|  |  | 50,000 F primary costs | Res. 71 (Rev. Marrakesh, 2002) |
| Lead Study Group for IP related matters, B-ISDN, |  | 274,000 F document costs | Strategic Plan for the Union 2004-2007 |
| Global Information Infrastructure and satellite matters |  |  |  |
|  |  |  | Res. 130 (Marrakesh, 2002) |
|  |  |  | Strengthening the role of ITU in information and |
|  |  | 5 Rapporteurs meetings | communication network security |
|  |  | of 5 days each |  |
| NGN |  |  |  |
| MPLS interworking |  |  |  |
| VPN (Virtual Private Network) |  |  |  |
| Integrated communication architecture, including the |  |  |  |
| impact of convergence |  |  |  |
| Interworking |  |  |  |
| Performance |  |  |  |
| New activity: |  |  |  |
| Joint Rapporteur Group (JRG) on NGN |  |  |  |
| 15 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| ICG SAT |  |  |  |
| Intersector Coordination Group on Satellite Matters |  |  |  |
| Under the Lead of SG 13 |  |  |  |
| Priorities: | Expected results: | 1 planned ICG-SAT meeting | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 3 working days | Strategic Plan for the Union 2004-2007 |
| To take into account satellite specificity within | Performance |  |  |
| telecommunication network including impact of | Achieved consistency of |  |  |
| IP-based network and multimedia network and system | Recommendations of various |  |  |
| Keeping up to date database | Study Groups for full integration |  |  |
|  | of the sat-transmission in |  |  |
| Coordination with ITU-R | public networks |  |  |
| The organization of a workshop will be considered |  |  |  |
| Strengthening relationship with ITU-D |  |  |  |
| SG 15 – Optical and other transport networks |  |  |  |
| Priorities: | Expected results: | 2 planned SG meetings | Res. 71 (Rev. Marrakesh, 2002) |
| Access Network | 60 Recommendations to be | and their WPs | Strategic Plan for the Union 2004-2007 |
| - broadband optical access, Multigigabit PONS | approved in 2005: 3,600 pages | 20 working days |  |
| - refinement & enhancement to SDL |  |  |  |
| - IP on Access Network |  | 6 P staff months |  |
| Network signal processing |  | 7 G staff months |  |
| - interaction of signal processing (OTN) |  | 221,000 F primary costs |  |
| Optical transport network structure |  | 2,747,000 F document costs |  |
| - automatic switched optical network (ASON) |  |  |  |
| - network management & control |  |  |  |
| OTN Technology |  |  |  |
| - coarse & dense wavelength division multiplexing (WDM) |  |  |  |
| - fiber characteristics |  |  |  |
| - transmission technology |  |  |  |
| - IP on WDM |  |  |  |
| Cooperation with IEC and other SDOs |  |  |  |
| Lead Study Group on access network transport |  |  |  |
| Lead Study Group on optical technology |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 16 - Multimedia services, systems and |  |  |  |
| terminals |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Rev. Marrakesh, 2002) |
| Multimedia communications and interworking |  | and its WPs | Strategic Plan for the Union 2004-2007 |
| (including IP and NGN) | 40 Recommendations to be | 9 working days |  |
| Security for Multimedia systems | approved in 2005: 1,500 pages |  | Res. 101 (Minneapolis, 1998): |
| Media Coding |  |  | Internet Protocol (IP)-based networks |
| Multimedia framework, MEDIACOM-2004 project |  | 8 P staff months |  |
| Telecommunications for Disaster Relief (TDR) |  | 8 G staff months |  |
| Accessibility for people with disabilities |  | 90,000 F primary costs |  |
|  |  | 773,000 F document costs |  |
| Cooperation with other Standard Development |  |  |  |
| Organization |  | 4 Rapporteur meetings |  |
| Lead Study Group on multimedia services, |  | 1 week each |  |
| systems and terminals |  |  |  |
| Lead Study Group on e-business and e-commerce |  |  |  |
| New activities: |  |  |  |
| E-commerce, E-business |  |  |  |
| E-health |  |  |  |
| 2 workshops |  | 3 days each |  |
| 23 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SG 17 - Data Networks and Telecommunication |  |  |  |
| Software |  |  |  |
| Priorities: | Expected results: | 2 planned SG meetings | Res. 71 (Rev. Marrakesh, 2002) |
| Communication System Security |  | and their WPs | Strategic Plan for the Union 2004-2007 |
| Development of a new OID database | 20 Recommendations to be | 18 working days |  |
| Addition to a set of Directory Recommendations | approved in 2005: 1,500 pages |  | Res. 130 (Marrakesh, 2002) |
| Complement to the set of ASN.1 Recommendations |  | 4 P staff months | Strengthening the role of ITU in information and |
| Language coordination and promotion |  | 10 G staff months | communication network security |
| Cooperation with ISO/IEC |  |  |  |
| Contribution to the coordination effort with ISO, IEC and |  | 88,000 F primary costs | Res. 101 (Minneapolis, 1998) |
| UN/ECE for E-business standardization |  | 795,000 F document costs | Collaborative activities on IP-based network with |
| Open Distributed Processing (ODP), Frame Relay |  |  | ISOC/IETF |
| Development of Framework Recommendations on Security |  |  |  |
|  |  |  | TSAG (Geneva, 19-23 March 2001) |
|  |  |  | TSAG approved the merger of Study group 7 and 10 |
| Lead Study Group on Frame Relay |  |  | into a single Study Group 17 |
| Lead Study Group on Communication System Security |  |  |  |
| Lead Study Group on Languages and Description |  | 15 Rapporteur meetings |  |
| Techniques |  | of 1 to 5 days each |  |
| Enhancement of communication system security |  |  |  |
| Further development of the ITU-T ASN.1 Project |  |  |  |
| Continuation of the provision of ASN.1 modules to the |  |  |  |
| ASN.1 database |  |  |  |
| Further development of the ITU-T language coordination |  |  |  |
| project |  |  |  |
| Further development of the ITU-T Security project |  |  |  |
| 2 workshops |  | 3 days |  |
| 27 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| SSG – Special Study Group IMT-2000 and beyond |  |  |  |
|  |  |  | Res. 38 (WTSA-2000) |
| Priorities: |  |  | Coordination among ITU-T, ITU-R and ITU-D for |
| Network aspects of IMT-2000 and beyond | Expected results: | 2 proposed SSG meetings | IMT-2000 activities |
| (International Mobile Telecommunications-2000) |  | 10 working days |  |
| Wireless access to IP-based networks | 6 Recommendations to be |  |  |
| Convergence of mobile and fixed networks | approved in 2005: 80 pages |  |  |
| Mobility management, mobile multimedia functions |  | 7 P staff months |  |
| Internetworking, interoperability | 1 Technical Report to be | 8 G staff months |  |
|  | approved in 2005: 40 pages | 37,000 F primary costs |  |
| Network vision of systems beyond IMT-2000 |  | 361,000 F document costs |  |
|  | 2nd Edition of Handbook on |  |  |
| Enhancement of ITU-T Recommendations on IMT-2000 | IMT-2000 to be approved in 2005: |  |  |
|  | 200 pages | 2 Rapporteur meetings |  |
| Lead Study Group on IMT-2000 and beyond |  | 7 working days |  |
| and for mobility |  |  |  |
|  |  | 1 Editor’s meeting |  |
| New activities: |  | 2 working days |  |
| Workshop on mobility group activities |  |  |  |
| Electronic meetings, electronic drafting groups |  | 4 electronic meetings |  |
|  |  | 40 days |  |
| 7 Questions |  | 1 workshop, 2 days |  |
| Workshops |  |  |  |
| Dissemination of expert knowledge on state-of-the-art | Expected results: | 25 P staff-months | Resolution 71 (Rev. Marrakesh, 2002): |
| technologies, |  | 7 G staff-months | Goal 3, 5, 6, Chapter 5 |
|  | New topics for Study Groups |  |  |
|  |  | 50,000 F primary costs: |  |
|  | Participation of delegates from | Fellowships for SG 3 |  |
| Promotion of awareness of ITU-T activities, | developing countries in the |  | Resolution 25 (Rev. Marrakesh, 2002) |
| working methods and priorities | activities of the Sector |  | Strengthening the regional presence |
|  | Strengthening regional presence |  | WTSA Resolution 17 (Montreal, 2000) |
| Exploring new topics |  |  | telecommunication standardization in relation |
|  | Achievement indicators: |  | to the interests of developing countries |
|  | Dissemination of expert technology |  |  |
|  |  |  | Council Resolution 1181 |
|  | Integration of developing countries |  | Recommendations on ITU Reform, WGR R7 |
|  | concerns in ITU-T outputs |  |  |
|  | Coordination of activities within |  | Council Resolution 1183 |
|  | Study Groups and with other SDOs |  | ITU regional presence |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Regional presence |  |  | Resolution 25 (Rev. Marrakesh, 2002) |
|  |  |  | Strengthening the regional presence |
| Strengthening the regional presence | Expected results: | 4 regional briefing meetings | “regional meetings should be organized in the various |
| Participation in external conferences |  | SG meetings in the regions | regions by the relevant Sectors, particularly ITU-D, in |
| Assistance to ITU-D | Strengthened regional presence | Workshops in the regions | order to improve the participation in and effectiveness |
|  | Awareness of ITU-T activities | Regional tariff group meetings | of the corresponding global meetings” |
|  |  |  | Resolution 123 (Marrakesh, 2002) |
|  |  |  | Bridging the standardization gap between developing |
|  |  |  | and developed countries |
|  | Achievement indicators: | 8 P staff-months | WTSA Resolution 17 (Montreal, 2000) |
| Organization of seminars in the field |  | 11 G staff-month | telecommunication standardization in relation |
| Assistance to the Regions | Membership satisfaction |  | to the interests of developing countries |
| Regional briefing meetings | Dissemination of ITU-T studies | 84,000 F primary costs |  |
|  | and Recommendations |  | Council Resolution 1183 |
|  |  |  | ITU regional presence |
|  |  |  | Resolution 71 (Rev. Marrakesh, 2002): |
| Promoting the ITU-T |  |  | Goal 3, 5, 6, Chapter 5 |
|  | Expected results: | 18 P staff-months | “to develop and execute a proactive plan, in |
| Press releases | Awareness of ITU-T activities | 9 G staff-month | collaboration with the secretariat, in order to promote |
| ITU-T presence in external events | Increased interest of Membership |  | the value of ITU-T in the face of competition from |
| Presentation of ITU-T activities during |  | 46,000 F primary costs | other standards bodies and to continue to enhance |
| external workshops | Achievement indicators: |  | efforts in this regards” |
| Promotion events | Higher number of Sector Members |  |  |
| Articles | Increased participation in the |  | Council Resolution 1181 |
| Promotional material | Sector activities |  | Recommendations on ITU Reform, WGR R7 |
| Website promotional content |  |  | “Recognizing the need to improve awareness of |
|  |  |  | ITU-T products and services, and the image of the |
|  |  |  | Union in general, Council instructs the Secretary- |
|  |  |  | General and the Director of the TSB to define and |
|  |  |  | implement a corresponding promotion strategy |
|  |  |  | and to allocate appropriate resources in the budget |
| External cooperation | Expected results: |  |  |
|  | Worldwide coordination | 9 P staff-months |  |
| Assistance to membership and Telecom community | Promotion of ITU-T activities | 11 G staff-months |  |
| Assistance and cooperation with other Sectors | Signature of MoUs |  |  |
| Liaison and coordination with international and regional | Achievement indicators: |  |  |
| organizations | Customer and membership |  |  |
| SDO cooperation | satisfaction |  |  |
| Participation in external conferences | Dissemination of ITU-T studies |  |  |
| IPR issues | and Recommendations |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts | Expected results: | 22 P staff-months |  |
|  |  | 151 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks |  |  |
| one month of approval. |  | 290,000 F primary costs | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 183,000 F invoiced costs | Strategic Plan for the Union 2004-2007 |
| Quickpub procedures | Key indicators: |  |  |
|  |  | Covered by sales revenues |  |
| Quality control of texts | Decrease time to edit publications |  |  |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 17 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 19,000 F primary costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: | Database development will be be strengthened as from 2005 |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 2 P staff-months |  |
|  | 3,000 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 156,000 F primary costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-month | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 400 UIPRN/UISCN reservations | 1 G staff-month | Cost recovery for some products and services |
|  | Achievement indicators: | 16,000 F primary costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2005 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |
| Bureau support |  |  |  |
| Membership |  | 32 P staff-months | Res. 72 (Rev. Marrakesh, 2002): Linking strategic, |
| Meeting organization and logistical support |  | 19 G staff-months | financial and operational planning in ITU |
| Document control |  |  |  |
| Administrative support |  | 10,374,000 F primary costs | Res. 104 (Minneapolis, 1998): |
| Finance and budget |  | 349,000 F document costs | Reduction of the volume and cost of documentation |
| Director Office |  |  | for ITU conferences |
| Internal management |  |  |  |
| Operational planning |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Gender perspective issues |  |  | Res. 70 (Rev. Marrakesh, 2002): |
|  |  |  | Gender mainstreaming in ITU |
| ###### Director’s Ad Hoc IPR Group |  | 2 planned meetings | Res. 1187 Council 2001 |
|  |  | 3 days | Gender perspective in ITU Human Resource |
|  |  |  | management policy and practice |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: |  |  |
| WEB development | Immediate posting of information | 25 G staff-months | Res. 1141 Council 1999 |
| Customer support (TSB helpdesk) |  |  | Reduction of the cost and volume of documentation for |
| Alternate Approval Process Implementation | Achievement indicators: |  | Conferences and Assemblies and the Council |
|  | Increased number of visitors |  |  |
|  | Customer satisfaction |  | Res. 32 (WTSA-2000) |
| Maintaining of the ITU-T Website and relevant information |  |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

___________________

Annex 5: Use of TSB resources in 2006 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Primary costs CHF (Draft ITU-T Budget) | Document costs CHF (Draft Gen. Sec. Budget) |
| --- | --- | --- | --- | --- |
| – TSAG (Telecommunication Standardization Advisory Group) 1 planned meeting, 5 working days | 8 | 6 | 88,000 | 79,000 |
| – Chairmen’ meetings: 1 planned meetings, 3 working days | 1 | 1 |  |  |
| – Study Group meetings: | 82 | 132 | 1,400,000 | 8,535,000 |
| 22 planned meetings, 153 working days |  |  |  |  |
| 12 Study Groups + Regional tariff groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 196 Questions under study |  |  |  |  |
| 246 new ITU-T Recommendations, |  |  |  |  |
| 13,480 pages of text |  |  |  |  |
| 13,546 pages of translation in F, E, S |  |  |  |  |
| 19,239 pages of translation in A, C, R |  |  |  |  |
| 19,444 pages of typing pool in F, E, S |  |  |  |  |
| 25,032 pages of typing pool in A, C, R |  |  |  |  |
| 12,000,000 pages of reprography |  |  |  |  |
| – Seminars and technical workshops: 12 planned workshops | 25 | 7 | 75,000 |  |
| – Regional presence: 4 regional briefing meetings Study Group meetings in the regions Workshops in the regions | 8 | 11 | 84,000 |  |
| – Promoting ITU-T activities | 18 | 9 | 46,000 |  |
| – External cooperation | 9 | 11 |  |  |
| – Study Group publications: 12,000 pages of Recommendations to be published per language | 22 | 151 | 281,000 | 183,000 |
| – Operational Bulletin: 24 issues a year | 17 | 16 | 19,000 | 20,000 |
| – Databases accessible to public | 5 | 3 |  |  |
| – UIFN registrar (Universal International Freephone Numbers) 3,000 UIFN | 2 | 13 | 156,000 |  |
| – UIPRN/UISCN registrar (Universal International Premium Rate Numbers) (Universal International Shared Cost Numbers) 400 UIPRN/UISCN | 1 | 1 | 16,000 |  |
| – Bureau support | 32 | 19 |  | 349,000 |
| – EDH (Electronic Document Handling) Documents & information posted on ITU Website |  | 25 |  |  |
| - Cost of TSB 230 P staff-months & 405 G staff-months |  = 230 |  = 405 | 10,383,000 |  |
| – Total of allocated resources |  |  | 12,548,000 | 9,166,000 |

Assumption: 10 staff-months per person per year

##### Annex 6: ITU-T - Linkage between Strategic, Financial and Operational Planning - 2006

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2006 budget | #### Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Telecommunication Standardization Advisory Group |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: |  |  |
| Reviews progress of work program & working methods |  | 1 planned meeting | Res. 18 (WTSA-2000) |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | with their working parties | Principles and procedures for the allocation of work |
| ITU-T) |  | 5 working days | to, and coordination between, the |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations |  | Radiocommunication and Telecommunication |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 8 P staff-months | Standardization Sectors |
| Advises on financial matters |  | 6 G staff-months |  |
| cooperation and coordination | Achievement indicators: |  | Res. 22 (WTSA-2000) |
|  |  | 88,000 F primary costs: | Authorization for TSAG to act between WTSAs |
|  | Minimized duplication of work | Interpretation, |  |
|  | Harmonized technical standards | Meeting staff | Res. 32 (WTSA-2000) |
|  | Enhanced operational efficiency |  | Strengthening the use of electronic document |
|  | of ITU-T | 79,000 F document costs : | Handling for the work of ITU-T |
|  |  | Translation, typing pool |  |
|  |  | Reprography | Res. 33 (WTSA-2000) |
|  |  | (Internal invoicing) | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 1 planned meeting |  |
| Finalization of meeting schedule for following year |  | 3 working days |  |
| Discussion on budget allocation on the various SG |  |  |  |
| Improvement in communication amongst SG |  | 1 P staff-month |  |
| Priority in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2006 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| Study Group Meetings | Expected results: | Total for all the Study Groups: |  |
| Study Group responsibility and mandates: | +/- 246 new ITU-T Recs. and other | 22 planned SG meetings | Article 17 of the Constitution |
| See WTSA-2004 | texts totaling about 13,480 pages | with their working parties |  |
|  | published in 6 languages | 153 working days | Article14 of the Convention |
|  | Development of a programme of |  |  |
|  | technical workshops | 82 P staff-months | Resolutions of Marrakesh, 2002 |
|  |  | 132 G staff-months | See below |
| 12 Study Groups + Regional tariff groups | Key performance indicators: | 1,400,000 F primary costs: |  |
| 1 Special Study Group |  | Interpretation |  |
| 196 technical, operating and tariff Questions under study | Worldwide utilization of ITU-T Recs. | Meeting staff |  |
|  | Text quality & market response | Mail expenses |  |
| Attention is paid to improvement of telecommunications | Reduction in time-to-market for | 8,535,000 F document costs |  |
| in developing countries and cooperation with national, | Recs (AAP implementation) | Total 6 languages: |  |
| regional and international organizations | Stability of texts and avoidance of | 32,785 pages of translation |  |
|  | document reprocessing | 44,476 pages of typing pool |  |
|  | Membership satisfaction | 12,000,000 pages of reprography |  |

| Workshops |  |  |  |
| --- | --- | --- | --- |
| Dissemination of expert knowledge on state-of-the-art | Expected results: | 25 P staff-months | Resolution 71 (Rev. Marrakesh, 2002): |
| technologies, |  | 7 G staff-months | Goal 3, 5, 6, Chapter 5 |
|  | New topics for Study Groups |  |  |
|  |  | 75,000 F primary costs: |  |
|  | Participation of delegates from | Fellowships for SG 3 |  |
| Promotion of awareness of ITU-T activities, | developing countries in the |  | Resolution 25 (Rev. Marrakesh, 2002) |
| working methods and priorities | activities of the Sector |  | Strengthening the regional presence |
|  | Strengthening regional presence |  | WTSA Resolution 17 (Montreal, 2000) |
| Exploring new topics |  |  | telecommunication standardization in relation |
|  | Achievement indicators: |  | to the interests of developing countries |
|  | Dissemination of expert technology |  |  |
|  |  |  | Council Resolution 1181 |
|  | Integration of developing countries |  | Recommendations on ITU Reform, WGR R7 |
|  | concerns in ITU-T outputs |  |  |
|  | Coordination of activities within |  | Council Resolution 1183 |
|  | Study Groups and with other SDOs |  | ITU regional presence |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2006 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Regional presence |  |  | Resolution 25 (Rev. Marrakesh, 2002) |
|  |  |  | Strengthening the regional presence |
| Strengthening the regional presence | Expected results: | 4 regional briefing meetings | “regional meetings should be organized in the various |
| Participation in external conferences |  | SG meetings in the regions | regions by the relevant Sectors, particularly ITU-D, in |
| Assistance to ITU-D | Strengthened regional presence | Workshops in the regions | order to improve the participation in and effectiveness |
|  | Awareness of ITU-T activities | Regional tariff group meetings | of the corresponding global meetings” |
|  |  |  | Resolution 123 (Marrakesh, 2002) |
|  |  |  | Bridging the standardization gap between developing |
|  |  |  | and developed countries |
|  | Achievement indicators: | 8 P staff-months | WTSA Resolution 17 (Montreal, 2000) |
| Organization of seminars in the field |  | 11 G staff-month | telecommunication standardization in relation |
| Assistance to the Regions | Membership satisfaction |  | to the interests of developing countries |
| Regional briefing meetings | Dissemination of ITU-T studies | 84,000 F primary costs |  |
|  | and Recommendations |  | Council Resolution 1183 |
|  |  |  | ITU regional presence |
|  |  |  | Resolution 71 (Rev. Marrakesh, 2002): |
| Promoting the ITU-T |  |  | Goal 3, 5, 6, Chapter 5 |
|  | Expected results: | 18 P staff-months | “to develop and execute a proactive plan, in |
| Press releases | Awareness of ITU-T activities | 9 G staff-month | collaboration with the secretariat, in order to promote |
| ITU-T presence in external events | Increased interest of Membership |  | the value of ITU-T in the face of competition from |
| Presentation of ITU-T activities during |  | 46,000 F primary costs | other standards bodies and to continue to enhance |
| external workshops | Achievement indicators: |  | efforts in this regards” |
| Promotion events | Higher number of Sector Members |  |  |
| Articles | Increased participation in the |  | Council Resolution 1181 |
| Promotional material | Sector activities |  | Recommendations on ITU Reform, WGR R7 |
| Website promotional content |  |  | “Recognizing the need to improve awareness of |
|  |  |  | ITU-T products and services, and the image of the |
|  |  |  | Union in general, Council instructs the Secretary- |
|  |  |  | General and the Director of the TSB to define and |
|  |  |  | implement a corresponding promotion strategy |
|  |  |  | and to allocate appropriate resources in the budget |
| External cooperation | Expected results: |  |  |
|  | Worldwide coordination | 9 P staff-months |  |
| Assistance to membership and Telecom community | Promotion of ITU-T activities | 11 G staff-months |  |
| Assistance and cooperation with other Sectors | Signature of MoUs |  |  |
| Liaison and coordination with international and regional | Achievement indicators: |  |  |
| organizations | Customer and membership |  |  |
| SDO cooperation | satisfaction |  |  |
| Participation in external conferences | Dissemination of ITU-T studies |  |  |
| IPR issues | and Recommendations |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2006 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts | Expected results: | 22 P staff-months |  |
|  |  | 151 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks |  |  |
| one month of approval. |  | 281,000 F primary costs | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 183,000 F invoiced costs | Strategic Plan for the Union 2004-2007 |
| Quickpub procedures | Key indicators: |  |  |
|  |  | Covered by sales revenues |  |
| Quality control of texts | Decrease time to edit publications |  |  |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 17 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 19,000 F primary costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2006 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: |  |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 2 P staff-months |  |
|  | 3,000 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 156,000 F primary costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-month | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 400 UIPRN/UISCN reservations | 1 G staff-month | Cost recovery for some products and services |
|  | Achievement indicators: | 16,000 F primary costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2006 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |
| Bureau support |  |  |  |
| Membership |  | 32 P staff-months | Res. 72 (Rev. Marrakesh, 2002): Linking strategic, |
| Meeting organization and logistical support |  | 19 G staff-months | financial and operational planning in ITU |
| Document control |  |  |  |
| Administrative support |  | 10,383,000 F primary costs | Res. 104 (Minneapolis, 1998): |
| Finance and budget |  | 349,000 F document costs | Reduction of the volume and cost of documentation |
| Director Office |  |  | for ITU conferences |
| Internal management |  |  |  |
| Operational planning |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Gender perspective issues |  |  | Res. 70 (Rev. Marrakesh, 2002): |
|  |  |  | Gender mainstreaming in ITU |
| ###### Director’s Ad Hoc IPR Group |  | 2 planned meetings | Res. 1187 Council 2001 |
|  |  | 3 days | Gender perspective in ITU Human Resource |
|  |  |  | management policy and practice |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: |  |  |
| WEB development | Immediate posting of information | 25 G staff-months | Res. 1141 Council 1999 |
| Customer support (TSB helpdesk) |  |  | Reduction of the cost and volume of documentation for |
| Alternate Approval Process Implementation | Achievement indicators: |  | Conferences and Assemblies and the Council |
|  | Increased number of visitors |  |  |
|  | Customer satisfaction |  | Res. 32 (WTSA-2000) |
| Maintaining of the ITU-T Website and relevant information |  |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

___________________

Annex 7: Use of TSB resources in 2007 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Primary costs CHF (Draft ITU-T Budget) | Document costs CHF (Draft Gen. Sec. Budget) |
| --- | --- | --- | --- | --- |
| – TSAG (Telecommunication Standardization Advisory Group) 2 planned meetings, 10 working days | 13 | 8 | 176,000 | 130,000 |
| – Chairmen’ meetings: 2 planned meetings, 4 working days | 1 | 1 |  |  |
| – Study Group meetings: | 77 | 130 | 1,400,000 | 8,535,000 |
| 22 planned meetings, 153 working days |  |  |  |  |
| 12 Study Groups + Regional tariff groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 196 Questions under study |  |  |  |  |
| 246 new ITU-T Recommendations, |  |  |  |  |
| 13,480 pages of text |  |  |  |  |
| 13,546 pages of translation in F, E, S |  |  |  |  |
| 19,239 pages of translation in A, C, R |  |  |  |  |
| 19,444 pages of typing pool in F, E, S |  |  |  |  |
| 25,032 pages of typing pool in A, C, R |  |  |  |  |
| 12,000,000 pages of reprography |  |  |  |  |
| – Seminars and technical workshops: 12 planned workshops | 25 | 7 | 75,000 |  |
| – Regional presence: 4 regional briefing meetings Study Group meetings in the regions Workshops in the regions | 8 | 11 | 84,000 |  |
| – Promoting ITU-T activities | 18 | 9 | 46,000 |  |
| – External cooperation | 9 | 11 |  |  |
| – Study Group publications: 12,000 pages of Recommendations to be published per language | 22 | 151 | 281,000 | 183,000 |
| – Operational Bulletin: 24 issues a year | 17 | 16 | 19,000 | 20,000 |
| – Databases accessible to public | 5 | 3 |  |  |
| – UIFN registrar (Universal International Freephone Numbers) 3,000 UIFN | 2 | 13 | 156,000 |  |
| – UIPRN/UISCN registrar (Universal International Premium Rate Numbers) (Universal International Shared Cost Numbers) 400 UIPRN/UISCN | 1 | 1 | 16,000 |  |
| – Bureau support | 32 | 19 |  | 349,000 |
| – EDH (Electronic Document Handling) Documents & information posted on ITU Website |  | 25 |  |  |
| - Cost of TSB 230 P staff-months & 405 G staff-months |  = 230 |  = 405 | 10,398,000 |  |
| – Total of allocated resources |  |  | 12,651,000 | 9,217,000 |

Assumption: 10 staff-months per person per year

##### Annex 8: ITU-T - Linkage between Strategic, Financial and Operational Planning - 2007

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2007 budget | #### Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Telecommunication Standardization Advisory Group |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: |  |  |
| Reviews progress of work program & working methods |  | 2 planned meetings | Res. 18 (WTSA-2000) |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | with their working parties | Principles and procedures for the allocation of work |
| ITU-T) |  | 10 working days | to, and coordination between, the |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations |  | Radiocommunication and Telecommunication |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 13 P staff-months | Standardization Sectors |
| Advises on financial matters |  | 8 G staff-months |  |
| cooperation and coordination | Achievement indicators: |  | Res. 22 (WTSA-2000) |
|  |  | 176,000 F primary costs: | Authorization for TSAG to act between WTSAs |
|  | Minimized duplication of work | Interpretation, |  |
|  | Harmonized technical standards | Meeting staff | Res. 32 (WTSA-2000) |
|  | Enhanced operational efficiency |  | Strengthening the use of electronic document |
|  | of ITU-T | 130,000 F document costs : | Handling for the work of ITU-T |
|  |  | Translation, typing pool |  |
|  |  | Reprography | Res. 33 (WTSA-2000) |
|  |  | (Internal invoicing) | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 2 planned meeting |  |
| Finalization of meeting schedule for following year |  | 4 working days |  |
| Discussion on budget allocation on the various SG |  |  |  |
| Improvement in communication amongst SG |  | 1 P staff-month |  |
| Priority in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2007 budget | #### Relationship to Strategic Policies and Plans |
| --- | --- | --- | --- |
| Study Group Meetings | Expected results: | Total for all the Study Groups: |  |
| Study Group responsibility and mandates: | +/- 246 new ITU-T Recs. and other | 22 planned SG meetings | Article 17 of the Constitution |
| See Res. 2 (WTSA-2000) | texts totaling about 13,480 pages | with their working parties |  |
|  | published in 6 languages | 153 working days | Article14 of the Convention |
|  | Development of a programme of |  |  |
|  | technical workshops | 77 P staff-months | Resolutions of Marrakesh, 2002 |
|  |  | 130 G staff-months | See below |
| 12 Study Groups + Regional tariff groups | Key performance indicators: | 1,400,000 F primary costs: |  |
| 1 Special Study Group |  | Interpretation |  |
| 196 technical, operating and tariff Questions under study | Worldwide utilization of ITU-T Recs. | Meeting staff |  |
|  | Text quality & market response | Mail expenses |  |
| Attention is paid to improvement of telecommunications | Reduction in time-to-market for | 8,535,000 F document costs |  |
| in developing countries and cooperation with national, | Recs (AAP implementation) | Total 6 languages: |  |
| regional and international organizations | Stability of texts and avoidance of | 32,785 pages of translation |  |
|  | document reprocessing | 44,476 pages of typing pool |  |
|  | Membership satisfaction | 12,000,000 pages of reprography |  |

| Workshops |  |  |  |
| --- | --- | --- | --- |
| Dissemination of expert knowledge on state-of-the-art | Expected results: | 25 P staff-months | Resolution 71 (Rev. Marrakesh, 2002): |
| technologies, |  | 7 G staff-months | Goal 3, 5, 6, Chapter 5 |
|  | New topics for Study Groups |  |  |
|  |  | 75,000 F primary costs: |  |
|  | Participation of delegates from | Fellowships for SG 3 |  |
| Promotion of awareness of ITU-T activities, | developing countries in the |  | Resolution 25 (Rev. Marrakesh, 2002) |
| working methods and priorities | activities of the Sector |  | Strengthening the regional presence |
|  | Strengthening regional presence |  | WTSA Resolution 17 (Montreal, 2000) |
| Exploring new topics |  |  | telecommunication standardization in relation |
|  | Achievement indicators: |  | to the interests of developing countries |
|  | Dissemination of expert technology |  |  |
|  |  |  | Council Resolution 1181 |
|  | Integration of developing countries |  | Recommendations on ITU Reform, WGR R7 |
|  | concerns in ITU-T outputs |  |  |
|  | Coordination of activities within |  | Council Resolution 1183 |
|  | Study Groups and with other SDOs |  | ITU regional presence |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2007 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Regional presence |  |  | Resolution 25 (Rev. Marrakesh, 2002) |
|  |  |  | Strengthening the regional presence |
| Strengthening the regional presence | Expected results: | 4 regional briefing meetings | “regional meetings should be organized in the various |
| Participation in external conferences |  | SG meetings in the regions | regions by the relevant Sectors, particularly ITU-D, in |
| Assistance to ITU-D | Strengthened regional presence | Workshops in the regions | order to improve the participation in and effectiveness |
|  | Awareness of ITU-T activities | Regional tariff group meetings | of the corresponding global meetings” |
|  |  |  | Resolution 123 (Marrakesh, 2002) |
|  |  |  | Bridging the standardization gap between developing |
|  |  |  | and developed countries |
|  | Achievement indicators: | 8 P staff-months | WTSA Resolution 17 (Montreal, 2000) |
| Organization of seminars in the field |  | 11 G staff-month | telecommunication standardization in relation |
| Assistance to the Regions | Membership satisfaction |  | to the interests of developing countries |
| Regional briefing meetings | Dissemination of ITU-T studies | 84,000 F primary costs |  |
|  | and Recommendations |  | Council Resolution 1183 |
|  |  |  | ITU regional presence |
|  |  |  | Resolution 71 (Rev. Marrakesh, 2002): |
| Promoting the ITU-T |  |  | Goal 3, 5, 6, Chapter 5 |
|  | Expected results: | 18 P staff-months | “to develop and execute a proactive plan, in |
| Press releases | Awareness of ITU-T activities | 9 G staff-month | collaboration with the secretariat, in order to promote |
| ITU-T presence in external events | Increased interest of Membership |  | the value of ITU-T in the face of competition from |
| Presentation of ITU-T activities during |  | 46,000 F primary costs | other standards bodies and to continue to enhance |
| external workshops | Achievement indicators: |  | efforts in this regards” |
| Promotion events | Higher number of Sector Members |  |  |
| Articles | Increased participation in the |  | Council Resolution 1181 |
| Promotional material | Sector activities |  | Recommendations on ITU Reform, WGR R7 |
| Website promotional content |  |  | “Recognizing the need to improve awareness of |
|  |  |  | ITU-T products and services, and the image of the |
|  |  |  | Union in general, Council instructs the Secretary- |
|  |  |  | General and the Director of the TSB to define and |
|  |  |  | implement a corresponding promotion strategy |
|  |  |  | and to allocate appropriate resources in the budget |
| External cooperation | Expected results: |  |  |
|  | Worldwide coordination | 9 P staff-months |  |
| Assistance to membership and Telecom community | Promotion of ITU-T activities | 11 G staff-months |  |
| Assistance and cooperation with other Sectors | Signature of MoUs |  |  |
| Liaison and coordination with international and regional | Achievement indicators: |  |  |
| organizations | Customer and membership |  |  |
| SDO cooperation | satisfaction |  |  |
| Participation in external conferences | Dissemination of ITU-T studies |  |  |
| IPR issues | and Recommendations |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2007 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts | Expected results: | 22 P staff-months |  |
|  |  | 151 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks |  |  |
| one month of approval. |  | 281,000 F primary costs | Res. 71 (Rev. Marrakesh, 2002) |
|  |  | 183,000 F invoiced costs | Strategic Plan for the Union 2004-2007 |
| Quickpub procedures | Key indicators: |  |  |
|  |  | Covered by sales revenues |  |
| Quality control of texts | Decrease time to edit publications |  |  |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 17 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 19,000 F primary costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2007 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: |  |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 2 P staff-months |  |
|  | 3,000 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 156,000 F primary costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-month | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 400 UIPRN/UISCN reservations | 1 G staff-month | Cost recovery for some products and services |
|  | Achievement indicators: | 16,000 F primary costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2007 budget | Relationship to Strategic Policies and Plans / PP-02 |
| --- | --- | --- | --- |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |
| Bureau support |  |  |  |
| Membership |  | 32 P staff-months | Res. 72 (Rev. Marrakesh, 2002): Linking strategic, |
| Meeting organization and logistical support |  | 19 G staff-months | financial and operational planning in ITU |
| Document control |  |  |  |
| Administrative support |  | 10,398,000 F primary costs | Res. 104 (Minneapolis, 1998): |
| Finance and budget |  | 349,000 F document costs | Reduction of the volume and cost of documentation |
| Director Office |  |  | for ITU conferences |
| Internal management |  |  |  |
| Operational planning |  |  | Res. 71 (Rev. Marrakesh, 2002) |
|  |  |  | Strategic Plan for the Union 2004-2007 |
| Gender perspective issues |  |  | Res. 70 (Rev. Marrakesh, 2002): |
|  |  |  | Gender mainstreaming in ITU |
| ###### Director’s Ad Hoc IPR Group |  | 2 planned meetings | Res. 1187 Council 2001 |
|  |  | 3 days | Gender perspective in ITU Human Resource |
|  |  |  | management policy and practice |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: |  |  |
| WEB development | Immediate posting of information | 25 G staff-months | Res. 1141 Council 1999 |
| Customer support (TSB helpdesk) |  |  | Reduction of the cost and volume of documentation for |
| Alternate Approval Process Implementation | Achievement indicators: |  | Conferences and Assemblies and the Council |
|  | Increased number of visitors |  |  |
|  | Customer satisfaction |  | Res. 32 (WTSA-2000) |
| Maintaining of the ITU-T Website and relevant information |  |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

___________________

DRAFT RESOLUTION

ROLLING FOUR-YEAR OPERATIONAL PLAN 
OF THE TELECOMMUNICATION STANDARDIZATION SECTOR 
FOR THE PERIOD 2004-2007

The Council,

recognising

the provisions of Article 15 of the Convention,

having considered

the rolling four-year Operational Plan of the Telecommunication Standardization Sector for the period of 2004-2007 (Document C04/10);

having also considered

the need of the Director of the Telecommunication Standardization Bureau to have some flexibility in the implementation of the rolling four-year Operational Plan so as to take into consideration any changes that may occur during the interval between two Council sessions,

resolves

to approve the rolling Operational Plan for the Telecommunication Standardization Sector for the years 2004-2007 as presented in Document C04/10, to undertake the activities of the TSB.

_______________